## Engagement Schedule
Engagement | Client | Audit Type | Year-End | Planning | Fieldwork Start | Fieldwork End | Final Review | Delivery Target | Lead Partner | Manager | Status
Fairmount Community Foundation — Financial Statement Audit | Fairmount Community Foundation | Financial Statement Audit | 2025-12-31 | 2025-02-15 | 2025-03-01 | 2025-04-15 | 2025-04-30 | 2025-05-15 | TBD | Imogen Carraway | Planning
Fairmount Community Foundation — Single Audit | Fairmount Community Foundation | Single Audit (Uniform Guidance) | 2025-12-31 | 2025-02-15 | 2025-03-01 | 2025-04-15 | 2025-04-30 | 2025-05-15 | TBD | Imogen Carraway | Planning
Rivergate Housing Trust — FY2025 Audit & Single Audit | Rivergate Housing Trust | Financial Statement & Single Audit | 2025-12-31 | 2025-02-20 | 2025-03-10 | 2025-04-30 | 2025-05-15 | 2025-06-01 | TBD | TBD | Planning
Kestrel Manufacturing 401(k) — Plan Year 2025 Audit | Kestrel Manufacturing | Plan Audit (DOL) | 2025-12-31 | 2025-01-30 | 2025-02-15 | 2025-03-30 | 2025-04-15 | 2025-04-30 | TBD | TBD | Planning
Cardinal Ridge Builders — FY2025 Audit | Cardinal Ridge Builders | Financial Statement Audit | 2025-12-31 | 2025-02-10 | 2025-02-25 | 2025-04-15 | 2025-04-30 | 2025-05-15 | TBD | TBD | Planning
Northwind Software — Quality of Earnings | Northwind Software | Special Project | 2025-12-31 | 2025-01-15 | 2025-02-01 | 2025-03-15 | 2025-03-30 | 2025-04-15 | TBD | TBD | Planning
Harbor Light Distribution — FY2025 Audit | Harbor Light Distribution | Financial Statement Audit | 2025-12-31 | 2025-02-01 | 2025-02-15 | 2025-04-15 | 2025-04-30 | 2025-05-15 | TBD | Imogen Carraway | Fieldwork Complete
Meridian Family Health — FY2025 Review | Meridian Family Health | Review Engagement | 2025-12-31 | 2025-02-20 | 2025-03-10 | 2025-04-15 | 2025-04-30 | 2025-05-15 | TBD | TBD | Planning
Stonebridge Property Group — FY2025 Audit | Stonebridge Property Group | Financial Statement Audit | 2025-12-31 | 2025-02-25 | 2025-03-15 | 2025-05-15 | 2025-05-30 | 2025-06-15 | TBD | TBD | Planning
Ashfield Pension Trust — FY2025 Audit | Ashfield Pension Trust | Plan Audit (DOL) | 2025-12-31 | 2025-02-05 | 2025-02-20 | 2025-04-15 | 2025-04-30 | 2025-05-15 | TBD | TBD | Planning

## Resource Allocation
Staff Member | Q1 Capacity (Hours) | Q2 Capacity (Hours) | Q3 Capacity (Hours) | Q4 Capacity (Hours) | Primary Engagements | Development Needs
Imogen Carraway | 180 | 160 | 140 | 160 | Fairmount FS/Single; Harbor Light; Engagement Lead | Mentoring—Fieldwork QC
Freya Holt | 160 | 150 | 180 | 170 | Fairmount; Rivergate; Cardinal Ridge | Advanced Testing—Revenue
Raj Malhotra | 150 | 140 | 170 | 160 | IT Audit coordination across engagements | System Architecture Assessment
Rosalind Calder | 170 | 160 | 150 | 170 | AR testing lead; Northwind QoE | Substantive Analytics—Development
Victor Alade | 160 | 150 | 160 | 170 | Kestrel 401(k); Ashfield Pension | Plan Audit Specialist Track
Priscilla Wong | 140 | 170 | 160 | 150 | Harbor Light sequencing; Stonebridge | Complex Transaction Analysis
Gabriel Fontes | 150 | 160 | 150 | 160 | Fairmount cutoff; Meridian review support | Engagement Junior Development
Owen Castile | 170 | 150 | 140 | 170 | GL modeling lead; Rivergate | Journal Entry Analysis—Advanced
Lucia Mendes | 160 | 150 | 170 | 160 | AR tie-out; Northwind support | Quality & Efficiency—Metrics
Sylvia Nakamura | 140 | 160 | 150 | 170 | Kestrel payroll/401(k); Ashfield | Plan Specialist—Deep Track
Colin Mackey | 150 | 140 | 160 | 150 | AR cross-check; Stonebridge AR | Workpaper QC—Advanced Methods

## Key Dependencies & Blockers
Engagement | Dependency | Owner | Status | Target Resolution | Risk Level
Fairmount FS & Single Audit | PBC documentation complete | Freya Holt | On Track | 2025-03-01 | Low
Harbor Light Distribution | GL cutoff testing lock | Owen Castile | Locked | Delivered | Resolved
Kestrel 401(k) | Payroll feed validation | Sylvia Nakamura | Locked | Delivered | Resolved
Rivergate Housing Trust | Entity setup & scope lock | Engagement Lead | Pending | 2025-02-28 | Medium
Northwind Software | Earnings model framework | Rosalind Calder | In Progress | 2025-02-15 | Medium
Ashfield Pension Trust | Prior-year findings follow-up | Victor Alade | In Progress | 2025-02-20 | Medium
Stonebridge Property Group | Complex transaction documentation | Priscilla Wong | Pending | 2025-03-01 | Medium
Meridian Family Health | Review scope clarification | Engagement Lead | Pending | 2025-02-28 | Low

## Internal Firm Initiatives
Initiative | Owner | Q1 Target | Q2 Target | Q3 Target | Q4 Target | Status
Audit Methodology Refresh | Firm Leadership | Kickoff & framework | Testing protocols | Tools & training | Rollout & feedback | In Progress
2026 Peer Review Prep | Firm Leadership | Engagement file review | Gap analysis | Remediation plan | Final QC & submission | Planning