## Active Engagements
Engagement | Client | Service | Status | Next Milestone | Owner | Risk Flag
tkt-000001 | Fairmount Community Foundation | FY2025 Financial Statement Audit | In Progress | Internal controls review – due 1/17 | Assigned
tkt-000002 | Fairmount Community Foundation | Single Audit (Uniform Guidance) | Pending | Awaiting GL reconciliation | Assigned | Dependent on -001
tkt-000003 | Rivergate Housing Trust | FY2025 Audit & Single Audit | In Progress | PBC follow-up due 1/15 | Assigned
tkt-000004 | Kestrel Manufacturing 401(k) | Plan Year 2025 Audit | In Progress | Participant census reconciliation – due 1/16 | Assigned
tkt-000005 | Cardinal Ridge Builders | FY2025 Audit | In Progress | New Location Setup ownership – LOCKED | Owen Castile | RESOLVED
tkt-000006 | Northwind Software | Quality of Earnings | In Progress | Data package validation – in progress | Victor Alade
tkt-000007 | Harbor Light Distribution | FY2025 Audit | In Progress | AR tie-out & cutoff testing – LOCKED | Nadia Osman
tkt-000008 | Meridian Family Health | FY2025 Review | Not Started | Scope & timeline TBD | Assigned | ⚠
tkt-000009 | Stonebridge Property Group | FY2025 Audit | In Progress | Reconciliation – LOCKED | Colin Mackey
tkt-000010 | Ashfield Pension Trust | FY2025 Audit | In Progress | Cutoff testing – LOCKED | Gabriel Fontes
tkt-000011 | Firm | 2026 Peer Review Preparation | Planning | Scoping document – due 1/20 | Victor Alade
tkt-000012 | Firm | Audit Methodology Refresh | Planning | Stakeholder alignment – due 1/22 | Victor Alade

## Critical Path – Next 48 Hours
Due Date | Engagement | Deliverable | Owner | Status
1/15/2025 | Rivergate Housing Trust | PBC Follow-up Documentation | Field Team | Pending
1/16/2025 | Kestrel Manufacturing 401(k) | Participant Census Reconciliation | Benefits Team | In Progress
1/17/2025 | Fairmount – FSA | Internal Controls Review Complete | Audit Team | On Track
1/20/2025 | Peer Review Prep | Scoping Document | Victor Alade | To Start

## Blockers & Dependencies
Issue | Related Engagement | Current Status | Action Required | Assigned To
GL sync timing | Fairmount Single Audit | Conditional – pending FSA completion | Schedule GL reconciliation post 1/17 | Elias Finch
New Location Setup ownership | Cardinal Ridge | RESOLVED – Real Estate locked as owner | Archive decision | Owen Castile
Meridian Family Health scope | Meridian FY2025 Review | Undefined | Confirm client expectations & timeline | Victor Alade

## Staff Availability & Capacity
Staff Member | Active Engagements | Locked Items This Week | Available Capacity | Notes
Owen Castile | Cardinal Ridge (lead) | New Location Setup | Medium | Real Estate sync Wed 14:30
Nadia Osman | Harbor Light (lead) | AR & cutoff testing | Low | Week compressed – protect evening
Colin Mackey | Stonebridge (lead) | Reconciliation | Low | Protect evening hours – in-season
Gabriel Fontes | Ashfield (lead) | Cutoff testing | Low | Protect evening hours – in-season
Lucia Mendes | Cross-project support | New Location Setup coordination | Medium | Ownership tracking role
Priscilla Wong | Cross-project support | AR coordination | Medium | GL sync dependency tracking
Victor Alade | Tax management + QoE + Peer Review | Data validation (QoE) | Low | ⚠ Review capacity