## PBC Tracker
PBC Item | Description | Requested | Due Date | Received | Status | Notes
GL-001 | General Ledger — 12/31/2025 | 2025-01-06 | 2025-01-13 |  | Outstanding | Standard trial balance export; Colin flagged GL sync with AR for Wed 14:30
AR-001 | Accounts Receivable — aged trial balance, 12/31/2025 | 2025-01-06 | 2025-01-13 |  | Outstanding | Colin confirmed AR locked; GL sync Wed 14:30 on track
AP-001 | Accounts Payable — aged trial balance, 12/31/2025 | 2025-01-06 | 2025-01-13 |  | Pending | Standard cutoff and reconciliation schedule
INV-001 | Inventory listing and valuation, 12/31/2025 | 2025-01-06 | 2025-01-17 |  | Outstanding | Cost of goods manufactured and FIFO/LIFO support
PPE-001 | Fixed asset register with 2025 additions and disposals | 2025-01-06 | 2025-01-17 |  | Pending | Depreciation schedule and capitalization policy documentation
BANK-001 | Bank confirmations — all accounts | 2025-01-06 | 2025-01-20 |  | Outstanding | Direct confirmation with financial institutions
DEBT-001 | Loan agreements and debt schedule reconciliation | 2025-01-06 | 2025-01-17 |  | Pending | Terms, covenants, and compliance testing
EQUITY-001 | Stockholder equity activity, 2025 | 2025-01-06 | 2025-01-13 |  | Outstanding | Share issuances, repurchases, dividend activity
PAYROLL-001 | Payroll register and tax reconciliation, full year 2025 | 2025-01-06 | 2025-01-17 |  | Outstanding | W-2 and payroll tax accrual tie-out
TRANS-001 | Transaction listing — all journal entries >$50k, full year | 2025-01-06 | 2025-01-20 |  | Outstanding | Supporting documentation for unusual or non-routine entries

## Testing Schedule
Test Area | Assigned To | Status | Target Completion | Notes
Revenue Recognition & AR | Theo Brandt | In Progress | 2025-01-24 | Waiting on GL/AR sync Wed 14:30; sample testing of invoicing and collections
Inventory Valuation | Theo Brandt | Pending PBC | 2025-01-31 | PBC due 01-17; tie-out to general ledger
Fixed Assets & Depreciation | Field Team | Pending PBC | 2025-01-31 | Physical verification and depreciation recalculation
Payroll & Benefits | Theo Brandt | Pending PBC | 2025-02-07 | Payroll reconciliation locked for sign-off per recent team confirmation
Cash & Bank Confirmations | Field Team | Pending PBC | 2025-02-07 | Direct confirmations; reconciliation of book to bank
Debt Covenants & Terms | Theo Brandt | Pending PBC | 2025-02-07 | Compliance testing and recalculation
Year-End Accruals | Field Team | Pending PBC | 2025-02-14 | Standard accrual and cutoff testing
Related Party & Subsequent Events | Theo Brandt | Pending PBC | 2025-02-14 | Management representation letter basis

## Key Dates
Milestone | Target Date | Owner | Status
GL/AR data sync & validation | 2025-01-15 (Wed 14:30) | Colin Mackey | On Track
PBC receipt — critical items (GL, AR, AP, EQ) | 2025-01-13 | Client Management | Outstanding
Fieldwork completion | 2025-02-21 | Theo Brandt / Field Team | In Progress
Audit committee communication | 2025-02-28 | Partner | TBD
Financial statements issued | 2025-03-07 | Partner | TBD