## PBC Status
Item | Description | Requested | Received | Status | Owner | Notes
AR Tie-out | Accounts receivable reconciliation to general ledger | Jan 8 | Jan 14 | Locked | Priscilla Wong / Nadia Osman | AR cutoff testing complete; October AR detail locked
GL Sync | General ledger reconciliation and post-cutoff review | Jan 8 | Pending | On Schedule | Elias Finch / Owen Castile | Scheduled Wed 14:30; completion extended to Thu EOD
Cutoff Testing | Revenue and expense cutoff documentation | Jan 8 | Jan 14 | Locked | Gabriel Fontes / Owen Castile | All cutoff testing locked; surety audit statements confirmed
Scope Documentation | Entity scope and service organization controls; surety audit statement requirements | Jan 8 | Jan 14 | Locked | Benedict (Partner) | Scope sign-off locked; surety audit statement requirements confirmed with Idris
Reconciliation Support | Reconciliation workpapers and tie-outs | Jan 8 | Jan 14 | Locked | Colin Mackey | Reconciliation solid and locked; cross-referenced
New Location Setup | Real Estate operations and finance setup documentation; statement dates and inventory procedures | Jan 8 | Jan 14 | Locked | Real Estate / Owen Castile / Maya Lindqvist | Ownership confirmed with Real Estate; locked with Real Estate, Ops, Finance; statement date and inventory count procedures locked

## Testing Progress
Testing Area | Planned | Completed | % Complete | Lead | Status | Issues
Accounts Receivable | Jan 13-14 | Jan 14 | 100 | Priscilla Wong / Nadia Osman | Locked | None
Cutoff Testing | Jan 13-14 | Jan 14 | 100 | Gabriel Fontes / Owen Castile | Locked | None
GL Reconciliation | Jan 14-15 | In Progress | 60 | Elias Finch / Owen Castile | On Schedule | Full sync Wed 14:30; completion extended to Thu EOD
New Location Setup Controls | Jan 14-15 | In Progress | 85 | Real Estate / Ops / Finance / Maya Lindqvist | On Schedule | Ownership confirmation resolved; statement dates and inventory count locked
Scope & SOC | Jan 8-10 | Jan 14 | 100 | Benedict | Locked | Surety audit statement requirements confirmed
Surety Audit Statements | Jan 13-14 | Jan 14 | 100 | Maya Lindqvist / Gabriel Fontes | Locked | Statement dates confirmed with Idris; audit requirements met

## Team Readiness
Team Member | Assigned to | Status | Last Update
Theo Brandt | PBC tracker & fieldwork lead | All set | Jan 14 — ready for Wed 14:30; fieldwork closeout Thu
Priscilla Wong | AR & cutoff | All locked | Jan 14 — AR locked; October detail confirmed
Nadia Osman | AR tie-out | Locked | Jan 14 — ready; October detail confirmed
Gabriel Fontes | Cutoff testing & surety statements | Locked | Jan 14 — surety audit statements locked
Owen Castile | GL sync & scope | All set | Jan 14 — GL sync scheduled Wed 14:30; extended to Thu
Colin Mackey | Reconciliations | All locked | Jan 14 — solid and cross-referenced
Elias Finch | GL support | On track | Jan 14 — full sync Wed 14:30; Thu completion
Maya Lindqvist | New Location Setup & surety statements | Locked with Real Estate | Jan 14 — statement dates locked; surety requirements confirmed
Rosalind Calder | Real Estate coordination | All locked | Jan 14 — Real Estate confirmed owner; statement dates set
Freya Holt | Support — Real Estate/Ops/Finance | All set | Jan 14 — inventory count date locked; Wed 14:30 ready
Lucia Mendes | New Location Setup ownership & procedures | Resolved | Jan 14 — ownership locked; statement procedures confirmed
Desmond Ortiz | Fieldwork support | All locked | Jan 14 — surety audit support confirmed; ready for Wed 14:30

## Key Dates
Event | Date | Time | Owner | Status
GL Sync & Post-Cutoff Procedures | Wednesday | 14:30 | Owen Castile / Elias Finch | Scheduled
New Location Setup Final Review | Wednesday | 14:30 | Real Estate / Ops / Finance / Maya Lindqvist | Scheduled; statement dates and inventory locked
GL Reconciliation Completion | Thursday | EOD | Elias Finch / Owen Castile | Extended; full sync completion
Surety Audit Statement Review | Wednesday | 14:30 | Benedict / Gabriel Fontes / Maya Lindqvist | Locked; requirements confirmed with Idris
Ready for Review & Fieldwork Closeout | Thursday Jan 16 | TBD | Theo Brandt | Planned; all core testing locked

## Review Points
Review Item | Owner | Target Date | Status
Surety audit statement dates and requirements | Maya Lindqvist / Benedict | Wed 14:30 | Confirmed; locked
Statement date alignment with inventory count | Real Estate / Lucia Mendes | Wed 14:30 | Locked
GL sync completion and post-cutoff sign-off | Owen Castile / Elias Finch | Thu EOD | On track
Fee model and phased delivery documentation | Maya Lindqvist / Desmond Ortiz | Wed 14:30 | Confirmed
Fieldwork closeout and final review readiness | Theo Brandt | Thu Jan 16 | Planned