## Remediation Costs
Cost Category | Q1 Actual | Q2 Actual | Q3 Actual | Q4 Actual | FY2025 Total | Budget | Variance | GL Account | Notes
Site Assessment & Testing | 12500 | 8750 | 6250 | 3500 | 31000 | 32000 | -1000 | 6410-Environmental | Soil and groundwater sampling complete
Remedial Action Plan Development | 5200 | 5200 | 5200 | 5200 | 20800 | 20000 | 800 | 6410-Environmental | Engineering consulting fees
Containment & Stabilization | 18900 | 22400 | 24100 | 19600 | 85000 | 85000 | 0 | 6420-Remediation Labor | On budget; site stabilization ongoing
Monitoring & Compliance Reporting | 3100 | 3100 | 3100 | 3100 | 12400 | 12000 | 400 | 6430-Compliance | Quarterly EPA submissions
Equipment & Materials | 9200 | 7800 | 6900 | 4200 | 28100 | 28500 | -400 | 6440-Equipment | Rental and consumables
Third-Party Lab & Testing | 4500 | 4800 | 5100 | 5600 | 20000 | 20000 | 0 | 6450-Testing | Baseline and confirmation sampling
Regulatory Permitting & Fees | 2800 | 0 | 0 | 0 | 2800 | 3000 | -200 | 6460-Permits | State DEP and local permits filed
Documentation & Record Management | 1200 | 1200 | 1200 | 1200 | 4800 | 5000 | -200 | 6470-Admin | Digital archival and compliance tracking
Subtotal Remediation Costs | 57500 | 54050 | 51850 | 42400 | 205800 | 205500 | 300
Contingency Reserve | 0 | 0 | 0 | 0 | 0 | 10000 | -10000 | 6480-Contingency | Not yet drawn
Total FY2025 Remediation | 57500 | 54050 | 51850 | 42400 | 205800 | 215500 | -9700 |  | GL tie-out complete; no exceptions

## GL Reconciliation
GL Account | Account Description | GL Balance | Workpaper Total | Difference | Reconciled | Prepared By | Date
6410 | Environmental Costs - Assessment | 31000 | 31000 | 0 | TRUE | Colin Mackey | 2025-01-15
6420 | Remediation Labor | 85000 | 85000 | 0 | TRUE | Colin Mackey | 2025-01-15
6430 | Compliance & Reporting | 12400 | 12400 | 0 | TRUE | Colin Mackey | 2025-01-15
6440 | Equipment & Materials | 28100 | 28100 | 0 | TRUE | Colin Mackey | 2025-01-15
6450 | Lab Testing Services | 20000 | 20000 | 0 | TRUE | Colin Mackey | 2025-01-15
6460 | Permits & Regulatory Fees | 2800 | 2800 | 0 | TRUE | Colin Mackey | 2025-01-15
6470 | Administrative & Record Mgmt | 4800 | 4800 | 0 | TRUE | Colin Mackey | 2025-01-15
Total | FY2025 Remediation Expense | 184100 | 184100 | 0 | TRUE | Colin Mackey | 2025-01-15

## Supporting Detail
Vendor | Invoice Date | Invoice Amount | GL Account | Paid Date | Check # | Supporting Docs
Remedial Science Partners LLC | 2025-01-10 | 12500 | 6410 | 2025-01-14 | 4521 | Testing reports filed
Meridian Engineering Group | 2024-12-28 | 5200 | 6420 | 2025-01-08 | 4518 | RAP draft v2 approved
Cleanup Solutions Inc. | 2025-01-12 | 18900 | 6420 | 2025-01-15 | 4523 | Monthly labor invoice Q1
Environmental Monitoring Corp | 2025-01-13 | 3100 | 6430 | 2025-01-15 | 4524 | Quarterly report submitted
Site Equipment Rentals | 2025-01-11 | 9200 | 6440 | 2025-01-14 | 4522 | Pump & tank rental receipt
Northeast Environmental Labs | 2025-01-09 | 4500 | 6450 | 2025-01-13 | 4520 | Lab analysis COC completed
State of CT DEP | 2024-12-15 | 2800 | 6460 | 2024-12-20 | 4510 | Permit filing confirmation
Internal Allocations | 2025-01-15 | 1200 | 6470 | 2025-01-15 |  | Per allocation schedule

## Review Points
Item | Status | Notes | Cross-Engagement Tie
GL Sync—Wed 14:30 | Locked | All remediation accounts reconciled and verified; AR locked; payroll locked per comms | Payroll & QoE locked; AR/GL sync confirmed Wed 14:30 with Victor, Priscilla, Theo; no cascading holds
Testing Extension | Recommended | Baseline & confirmation sampling (6450) nominal; post-close Q4 closure testing recommended per engagement calendar; testing files locked and ready per Theo | QoE locked; post-close confirmation labs do not cascade to Wed sync; recommend release post-final sign-off
Contingency Reserve (6480) | Not Yet Drawn | $10k reserve remains; evaluate vs. final close variance timing per Loop & Ladder Thursday review | Contingency release alignment with final sign-off pending Thursday pair session (Desmond & Maya, 15:00)
Permit & Regulatory Status | Complete | State DEP and local permits filed Dec 2024; no outstanding regulatory holds; compliance locked for Wed payroll sync | Compliance locked per engagement sequence; K-1 and posting summary locked per Lucia; no regulatory cascade items