## Active Queue
Engagement | Client | Service | Status | Next Step | Due | Owner | Blocked?
tkt-000001 | Fairmount Community Foundation | FY2025 Audit | GL sync locked Wed 14:30 | Team executes sync; Maya pulls trial balance | 12/20 | maya-lindqvist | FALSE
tkt-000002 | Fairmount Community Foundation | Single Audit (UG) | POC workpaper locked | Awaiting GL sync Wed 14:30 | 12/20 | maya-lindqvist | FALSE
tkt-000003 | Rivergate Housing Trust | FY2025 Audit & Single Audit | GL sync locked Wed 14:30 | Team ready to execute | 12/20 | rosalind-calder | FALSE
tkt-000004 | Kestrel Manufacturing 401(k) | Plan Year 2025 Audit | Payroll reconciliation locked | 401(k) testing files locked | 12/18 | sylvia-nakamura | FALSE
tkt-000005 | Cardinal Ridge Builders | FY2025 Audit | Testing files locked | Awaiting GL sync Wed 14:30 | 12/20 | theo-brandt | FALSE
tkt-000006 | Northwind Software | Quality of Earnings | QoE system blocker — IT escalated | Awaiting IT ETA; blocking POC | 12/22 | colin-mackey | TRUE
tkt-000007 | Harbor Light Distribution | FY2025 Audit | POC calcs locked; variance narrative clear | Awaiting GL sync Wed 14:30 | 12/20 | owen-castile | FALSE
tkt-000008 | Meridian Family Health | FY2025 Review | K-1 prep locked | Awaiting GL sync Wed 14:30 | 12/20 | lucia-mendes | FALSE
tkt-000009 | Stonebridge Property Group | FY2025 Audit | GL sync locked Wed 14:30 | Team ready to execute | 12/20 | gabriel-fontes | FALSE
tkt-000010 | Ashfield Pension Trust | FY2025 Audit | Remediation plan locked; scope call scheduled | Awaiting scope call output | 12/20 | victor-alade | FALSE
tkt-000011 | Firm | 2026 Peer Review Prep | Planning phase | Coordinate with leadership | 01/31 | victor-alade | FALSE
tkt-000012 | Firm | Audit Methodology Refresh | Planning phase | Coordinate with leadership | 02/28 | victor-alade | FALSE

## Blockers & Risks
Blocker | Engagement | Impact | Assigned To | ETA | Severity
QoE system error | tkt-000006 Northwind Software | POC calc & validation blocked; AR tie-out stalled | IT Support | TBD | High
Stale doc (3+ days unfiled) | tkt-000002 Fairmount Single Audit | Review queue backlog risk | victor-alade | Today | Medium

## GL Sync Execution
Date/Time | Clients | Responsible | Status
Wed 12/18 14:30 | Fairmount (tkt-000001), Rivergate (tkt-000003), Cardinal Ridge (tkt-000005), Harbor Light (tkt-000007), Meridian (tkt-000008), Stonebridge (tkt-000009) | Team (Maya pulls TB) | Locked & confirmed