## Fee Estimate Summary
Phase / Workstream | Prior Estimate ($) | Fees Incurred to Date ($) | Revised Estimate to Complete ($) | Revised Total Estimate ($) | Variance vs Prior ($) | Notes
Due Diligence | 85000 | 78500 | 6000 | 84500 |  | Substantially complete; residual for outstanding follow-ups
Corporate / Structuring | 45000 | 41000 | 5000 | 46000 |  | Closing checklist finalized; minor drafting remains
Real Estate / Estoppels | 30000 | 27500 | 9500 | 37000 |  | Whitfield estoppel escalated past Dov per read-aloud-to-CC policy; additional partner time reserved
Financing / Lender Coordination | 20000 | 18000 | 2000 | 20000 |  | On track, no change
Regulatory / Good Standing | 8000 | 8000 | 0 | 8000 |  | Good standing confirmed closed 12/12; no further action
Closing / Post-Closing | 25000 | 6000 | 19000 | 25000 |  | Closing set preparation in progress
Total

## Whitfield Estoppel Detail
Item | Status | Owner | Escalation Level | Fee Impact ($) | Notes
Estoppel deadline letter | Escalated — underway (not contingency) | Quentin (lead), Samir/Lucien cc | Past Dov — read-aloud-to-CC policy | 4500 | No further action required from Samir/Lucien beyond status tracking
Counsel call re: Whitfield status | Follow-up tied to call outcome | Dov | Active | 3000 | Written estoppel follow-up contingent on call result
Good standing certificate | Closed | N/A | N/A | 0 | Confirmed closed 12/12
MIP Item #10 | Closed | N/A | N/A | 0 | Confirmed closed per closing checklist