## Slide 1: Overview: Chain-of-Access Docket Status
Purpose: current status of open items tied to the Ardmore Elevator chain-of-access matter
Three substantive items remain open pending sign-off
One scheduling conflict has been resolved administratively
Deadline discipline: dates calendared from governing source, not from verbal assurance

## Slide 2: Open Item 1: Written-Direction Date
Status: outstanding, pending sign-off
No deadline change as a result of today's scheduling resolution
Remains tracked on the active docket pending confirmation

## Slide 3: Open Item 2: Review-Completion Date
Status: outstanding, pending sign-off
Unaffected by administrative scheduling matters resolved today
Remains tracked on the active docket pending confirmation

## Slide 4: Open Item 3: Internal Call Date / Roland's Availability
Status: outstanding, pending sign-off
Dependent on Roland's availability being confirmed
Unaffected by administrative scheduling matters resolved today

## Slide 5: Closing: Docket Review Note
Duplicate 9:00 / 9:30 bookings for the Ardmore chain-of-access routing decision have been resolved
Confirmed via chat with R. Duchamp: 9:00 slot is canonical; 9:30 cancelled
Samir has been notified of the 9:00 canonical slot
Ownership clarified per B. Ashworth: chain-of-access routing decision belongs to Samir, not Bennett
Lucien's separate item (ticket tkt-ardmore-elevator-good-standing) is tracked apart from the three open sign-off items above; ownership unchanged per exchange with Lucien
This is an administrative scheduling confirmation only — carries no deadline
Does not affect the three outstanding open items above, which remain pending sign-off
Notes: Reformatted from prior document-labeled version per today's flagged formatting issue; content otherwise unaltered.