## Conditions Precedent
Item | Category | Owner | Status | Target Date | Initials | Notes
Odell estoppel certificate | Estoppel | Ingrid | In progress | EOD today |  | No pushback on terms reported; awaiting execution/delivery
Whitfield estoppel certificate | Estoppel | Quentin | In progress | EOD today |  | No pushback on terms reported; second estoppel gates firm close-date announcement
Sandhurst good-standing certificate (jurisdiction outstanding) | Corporate diligence | Samir | Escalating | EOD today |  | Outstanding jurisdiction issue being escalated by Samir
MIP mechanics reconciliation — corrected draft receipt confirmation (Whitfield/Sandhurst) | MIP / Purchase Price Mechanics | Quentin / Samir / Ingrid | Open — unconfirmed | EOD today |  | Corrected draft sent; no confirmed receipt yet. Not closed until supplier file goes out and Whitfield/Sandhurst confirm directly (not secondhand via Quentin)
Environmental exposure — firm dollar figure and cost allocation | Price/Cost Adjustment | Dov | Open — pending figure | Tomorrow EOD |  | Treated as price/cost item, not a walk-away condition; no indication of closing delay
Closing date — final confirmed date | Scheduling | Dov | Open — pending second estoppel | Tomorrow EOD |  | To be issued same-day once second estoppel (Whitfield) lands
Supplier counterclaim / dispute posture | Litigation risk | Imelda / Dov | Resolved — hold as defense | N/A | N/A | Advised against filing counterclaim now; recovery speculative, no firm damages number; distraction risk only, not timeline risk. Damages estimate scoping available on request, not board-meeting ready
Ravenna response on outstanding item | Diligence | Ulrich | Unresponsive | TBD |  | Continuing to chase; will report on movement
Signature page circulation | Execution | Dov | Held | Pending all CPs |  | Will not circulate until every condition precedent above carries owner initials

## Escalation Protocol
Trigger | Rule | Owner
Any counterparty delay or non-response on Odell or Whitfield items | 30-minute escalation rule; immediate flag to Dov | Ingrid / Quentin / Samir
MIP mechanics receipt confirmation | Direct yes/no required from Whitfield/Sandhurst; secondhand confirmation via Quentin not acceptable | Ingrid