# End-of-Day Docket Sweep — 4/3

Prepared by T. Mokoena, Docket & Calendar Manager. Status reflects docket text and direct confirmations as of 16:30 ET. Two items remain unresolved and are escalated below.

## Escalated Item 1: Ardmore Good Standing Filing

Deadline: 4/2, 4:00 PM ET — MISSED. Days remaining: 0. Filing did not go out before the clerk's cutoff and is now queued for tomorrow's clerk window (4/4).

Owner: Lucien, confirmed as of today following the missed cutoff. Ownership was reassigned from the Deshmukh/Ardmore-adjacent matter; this is a staffing/ownership confirmation only and carries no new deadline of its own.

Days-elapsed tracking carries forward from the original 4/2 deadline rather than resetting on reassignment. Lucien has been asked directly for a remediation date; none received as of this sweep.

Status: OPEN — ESCALATED. No remediation date on file.

## Escalated Item 2: Jamal Non-Privilege Sign-Off (Ardmore/Whitfield)

Deadline: tonight, EOD 4/3. Days remaining: 0.

This item originated as a separate flag raised by Lucien, distinct from the Ardmore good standing filing split. Scope was confirmed as Jamal's non-privilege confirmation on Ardmore/Whitfield and logged as its own line item.

Jamal was chased directly twice today with the tonight-EOD, 0-days-remaining deadline restated each time. No confirmation received as of this sweep.

Ownership update: Bennett has acknowledged taking ownership of this sign-off. New deadline confirmed as EOD tomorrow (4/4). This supersedes the tonight-EOD deadline for calendaring purposes; the missed 4/3 deadline is logged below as a slip.

Status: OPEN — ESCALATED, reassigned to Bennett, new deadline 4/4 EOD.

## Related, Out of Scope: Deshmukh/Ardmore-Adjacent

Remains out of scope pending Jamal's confirmation on the non-privilege point above. Logged separately from the Ardmore good standing filing. Filing responsibility on this thread was confirmed reassigned to Lucien — staffing confirmation only, no new deadline, and does not affect the three open calendar items tracked on this matter (written-direction date, Position Statement review-completion date, internal call date/Roland's availability).

## Docket Status Table — All Open Matters

| Matter | Item | Deadline | Days Remaining | Owner | Status |
| --- | --- | --- | --- | --- | --- |
| Ardmore/Whitfield | Good standing filing (missed 4/2 4pm) | 4/4 clerk queue | 0 (elapsed carried forward) | Lucien | Open — Escalated |
| Ardmore/Whitfield | Non-privilege sign-off (Jamal item) | 4/4 EOD | 1 | Bennett | Open — Escalated, reassigned |
| Ardmore/Whitfield (Deshmukh-adjacent) | Written-direction date | Pending | Pending | TBD | Open |
| Ardmore/Whitfield (Deshmukh-adjacent) | Position Statement review-completion date | Pending | Pending | TBD | Open |
| Ardmore/Whitfield (Deshmukh-adjacent) | Internal call date (Roland's availability) | Pending | Pending | TBD | Open |

## Next Steps

Confirm 4/4 clerk queue filing of Ardmore good standing item; obtain remediation date from Lucien.

Chase Bennett for non-privilege sign-off ahead of 4/4 EOD deadline.

Hold Deshmukh/Ardmore-adjacent items open pending resolution of the non-privilege confirmation.

No action required on Deshmukh/Ardmore filing reassignment note — logged for record only, no calendar change.

Source note: all deadlines above are calendared from court docket text where applicable, not from attorney representations. Sharing: open, per standard practice.