# End-of-Day Docket Sweep — 4/2

Prepared by Thandiwe Mokoena, Docket & Calendar Manager. This sweep logs the status of all open docket items as of close of business 4/2.

## Closed Today

### Ardmore Good Standing Filing

Status: CLOSED. Confirmed in good standing as of today, 4/2. Confirmation received from Rosalie, Hyun-woo, and Lucien Abara. Original deadline was 4:00pm on 3/31; that deadline was missed and the item carried forward under Lucien's ownership following the 3/31 escalation. Days elapsed at time of closure: 2. No further action required; item is removed from tomorrow's sweep.

## Still Open

### Ardmore/Whitfield Non-Privilege Sign-Off

Status: OPEN. Awaiting Jamal's confirmation on the non-privilege point flagged by Lucien Abara and separated from the Ardmore Good Standing Filing item. Deadline: tonight, 4/2, EOD. Days remaining: 0. Chased Jamal directly today with no response received. Will escalate to the docket channel tomorrow morning if no confirmation is received tonight.

## Out of Scope — Monitoring Only

### Deshmukh Matter

Status: OUT OF SCOPE, pending Jamal's confirmation. Logged separately from the Ardmore Good Standing Filing per Lucien's 3/31 clarification. No deadline currently assigned. Will be re-evaluated once Jamal's confirmation on the Ardmore/Whitfield non-privilege point is received.

## Escalation Log

| Date | Item | Escalated To | Note |
| --- | --- | --- | --- |
| 3/31 | Position Statement sign-off ownership | Docket channel | Renewed escalation after repeated unanswered chases to Jamal; EOD deadline restated. |
| 3/31 | Ardmore Good Standing Filing — missed 4:00pm deadline | Hyun-woo, Rosalie | Demanded written confirmation of status same day; logged regardless of response. |
| 4/1 | Ardmore Good Standing Filing — ownership transfer | Lucien Abara | Confirmed Lucien as owner following missed cutoff; days elapsed carried forward, not reset. |
| 4/2 | Ardmore/Whitfield non-privilege sign-off | Jamal | Chased directly; deadline tonight EOD, 0 days remaining, no response as of sweep. |

## Cross-Check Notes

Ardmore Good Standing Filing confirmed closed per Rosalie, Hyun-woo, and Lucien; verified against court/registry docket text, not attorney representation alone.

Ardmore/Whitfield non-privilege item remains distinct from the closed Good Standing Filing item; do not conflate the two in tomorrow's sweep.

Deshmukh matter remains out of scope pending Jamal's confirmation on the Ardmore/Whitfield point; will move to active tracking once that confirmation lands.

Position Statement sign-off ownership question remains unresolved as of this sweep; carrying forward for continued monitoring.