## Summary
Engagement | Budget | Actual Fees | Overage $ | Overage % | Primary Driver
Coastal Meridian - Covenant Timing / Waterfall | 85000 | 118750 |  |  | Additional covenant-timing and waterfall reconciliation work (base + downside cases) not in original scope
Ravenna - Estoppel Count / Diligence | 42000 | 61300 |  |  | Estoppel count expanded scope pending Quentin's review
Farraday - No Changes Review | 15000 | 14200 |  |  | Closed as no changes; under budget, released
Total

## Coastal Meridian Detail
Timekeeper | Role | Budgeted Hours | Actual Hours | Rate | Budgeted Fees | Actual Fees | Variance $
Dov | Senior Associate | 90 | 132 | 650
Saoirse | Associate | 60 | 84 | 495
Quentin | Counsel | 20 | 27 | 725
Adaora | Partner (oversight) | 5 | 9 | 950
Total

## Ravenna Detail
Timekeeper | Role | Budgeted Hours | Actual Hours | Rate | Budgeted Fees | Actual Fees | Variance $
Quentin | Counsel | 40 | 62 | 725
Saoirse | Associate | 20 | 25 | 495
Total

## Narrative Notes
Topic | Explanation
Coastal Meridian overage - root cause | Original budget assumed a single covenant-timing read against the term sheet. Dov's analysis required threshold corrections to Section 4.2 (final markup) first, then a full waterfall reconciliation against both base and downside cases, which was not priced into the original scope. This added an estimated 40+ hours across Dov and Saoirse.
Coastal Meridian overage - timing | Base-case model inputs were sent to Dov and Saoirse to run the reconciliation; downside stress test follows once base case is confirmed. Amendment history and fully executed agreement are being delivered together Thursday EOD, contingent on Quentin's estoppel count landing without slippage.
Ravenna overage - root cause | Estoppel count under Quentin expanded beyond original diligence scope; this is the pacing item for the Coastal Meridian covenant-timing read and is being tracked for same-day notice if it slips.
Farraday - closed | Released as no changes; matter closed under budget, no overage to explain.
Write-off authority note | No write-off is being requested here. If any portion of the Coastal Meridian or Ravenna overage is ultimately written off above $25,000, that will come to Adaora in writing with the reason included in the same message, per firm policy.