## Review Status Log
Batch ID | Custodian | Docs Loaded | Docs Reviewed | Responsive | Privileged | Reviewer | Status | Last Updated | Notes
BATCH-01 | T. Renwick | 842 | 842 | 231 | 44 | N. Haddad | Complete | 2025-01-14 | First-level review complete; QC pending
BATCH-02 | T. Renwick (email) | 1560 | 1560 | 402 | 118 | N. Haddad | Complete | 2025-01-16 | Includes personal device export
BATCH-03 | Halden IT — shared drive | 2103 | 2103 | 190 | 12 | N. Haddad | Complete | 2025-01-17 | Mostly non-responsive HR templates
BATCH-04 | M. Osei (VP Sales) | 977 | 977 | 288 | 61 | N. Haddad | Complete | 2025-01-20 | Several docs flagged for privilege log
BATCH-05 | J. Calder (former GM) | 1240 | 604 | 140 | 9 | N. Haddad | In progress | 2025-01-22 | Second-level QC needed before status change
BATCH-06 | Renwick — text/SMS export | 315 | 0 | 0 | 0 | Unassigned | Not started | 2025-01-10 | Awaiting vendor load confirmation

## Summary
Metric | Value
Total Docs Loaded
Total Docs Reviewed
Total Responsive
Total Privileged (to log)
Percent Reviewed
Batches Not Started | 1
Batches In Progress | 1
Batches Complete | 4

## Document Status Log
Date | Batch/Doc Reference | Change | Made By | Reason
2025-01-14 | BATCH-01 | Marked Complete | N. Haddad | First-level review finished, no QC exceptions
2025-01-17 | BATCH-03 | Marked Complete | N. Haddad | Confirmed non-responsive via keyword sampling
2025-01-20 | BATCH-04 | Flagged for privilege log | N. Haddad | 61 docs contain in-house counsel correspondence
2025-01-21 | doc-000003 | Status verified — confirmed as final | N. Haddad | Cross-checked against filing draft; matches current review status
2025-01-22 | BATCH-05 | Held at In Progress | N. Haddad | QC pass incomplete; do not represent as done until second reviewer signs off
2025-01-10 | BATCH-06 | Held at Not Started | N. Haddad | Vendor has not confirmed load; do not assign reviewer yet
2025-01-23 | Privilege Log Nos. 5 and 8 | Marked Resolved | N. Haddad | Per confirmation from Hyun-woo that both items are resolved