## Production Plan
Custodian | Data Source | Doc Count (Est.) | Review Status | Responsive Rate | Privilege Review Status | Production Deadline | Owner | Notes
R. Pryor | Email (Legacy Outlook PST) | 14200 | Complete | 22% | Complete | 2025-05-30 | H. Bae | See record — custodial cert executed 5/12
R. Pryor | Local Drive / Laptop Image | 3100 | Complete | 18% | Complete | 2025-05-30 | H. Bae | Includes CAD design files flagged for expert review
Linden Eng. Team (5 custodians) | Shared Drive / Confluence | 41500 | In Progress | TBD | Not Started | 2025-06-13 | N. Haddad | Section I integration issue raised by Hyunwoo — still under review; cross-referenced against unidentified docket entry flagged by Thandiwe Mokoena (see Deadline Tracker notes). Haddad confirms de-dup against email in progress, unresolved as of last check-in
Linden Eng. Team (5 custodians) | Slack Export | 9800 | In Progress | TBD | Not Started | 2025-06-13 | N. Haddad | De-duplication against email running now; no change since last status
IT / Systems Admin | Server Logs (Access Records) | 2200 | Not Started | TBD | Not Started | 2025-06-13 | R. Duchamp | Needed to establish access timeline for misappropriation claim; Duchamp separately involved in resolving unidentified docket entry thread (ruled out Sable Ridge connection)
Former VP Eng. (departed) | Email + Device Image | 6700 | Not Started | TBD | Not Started | 2025-06-20 | H. Bae | Preservation letter sent 4/2; awaiting forensic vendor pickup

## Privilege Log
Doc ID Range | Custodian | Date | Author | Recipients | Privilege Basis | Description | Reviewer
PRIV-0001 to PRIV-0047 | R. Pryor | 2024-11-04 | Outside Counsel (Trade Secret Opinion) | R. Pryor; GC Linden | Attorney-Client / Work Product | Legal advice re: scope of confidentiality obligations under prior employment agreement | N. Haddad
PRIV-0048 to PRIV-0112 | Linden Eng. Team | 2024-12-01 to 2025-01-15 | In-House Counsel | Engineering leads | Attorney-Client | Advice regarding internal investigation into design file access | H. Bae
PRIV-0113 to PRIV-0140 | Former VP Eng. | 2025-01-20 | Outside Counsel (Litigation) | Former VP Eng.; GC Linden | Work Product | Litigation hold strategy and anticipated claims analysis | N. Haddad

## Deadline Tracker
Milestone | Court-Ordered Deadline | Internal Target | Status | Responsible
Custodian Interviews Complete | 2025-05-16 | 2025-05-12 | Complete | H. Bae
Search Term Negotiation w/ Opposing Counsel | 2025-05-23 | 2025-05-20 | Complete | B. Ashworth
First Rolling Production | 2025-06-06 | 2025-06-04 | On Track | N. Haddad
Privilege Log Service | 2025-06-13 | 2025-06-11 | At Risk — Section I dependency; unresolved docket entry under active investigation by Thandiwe Mokoena, with input from Lucien Abara, Rosalie Duchamp, Jamal Okonkwo, and Hyunwoo Bae — see record | N. Haddad
Final Production Complete | 2025-06-20 | 2025-06-18 | Pending | B. Ashworth
Unidentified Docket Entry — Resolution | TBD | 2025-06-06 | In Progress — ruled out Sable Ridge per R. Duchamp; awaiting Lucien Abara confirmation on remaining leads | T. Mokoena