## Open Items
Item # | Category | Description | Owner | Priority | Status | Date Opened | Date Due | Notes
1 | Corporate | Confirm Sandhurst add-on target cap table fully diluted, including outstanding options/warrants | Q. Sarr | High | Open | 2024-05-01 | 2024-05-17 | Requested updated cap table from target counsel; still awaiting response as of 2024-05-14 per chat with I. Solheim ("still nothing back"). Escalated at Whitfield Estoppel Escalation working session; Whitfield Counterparty Counsel has still not responded to renewed request as of the working session. MIP mechanics reconciliation (Item #10) confirmed and no longer blocked on this item, but cap table still required to finalize fully diluted share count. Due date extended two days pending resolution; re-escalation now in progress via working session follow-up
2 | Financial | Reconcile target EBITDA add-backs against QoE report | M. Feld | High | In Progress | 2024-05-01 | 2024-05-17 | QoE received; reconciling with management adjustments
3 | Contracts | Review material customer contracts for change-of-control and assignment provisions | Q. Sarr | High | Open | 2024-05-02 | 2024-05-16 | 12 of 20 contracts reviewed
4 | Contracts | Review material supplier contracts for change-of-control and assignment provisions | Q. Sarr | Medium | Open | 2024-05-02 | 2024-05-18 | Supplier list still incomplete; following up with target
5 | Employment | Confirm key employee retention agreements and non-compete coverage | R. Okafor | High | Open | 2024-05-03 | 2024-05-16 | Draft retention terms circulated to Northmoor HR lead
6 | IP | Confirm ownership/assignment of core software IP from founder to target entity | L. Barsanti | High | Open | 2024-05-03 | 2024-05-17 | Assignment agreement located; confirming recordation
7 | Real Estate | Review facility leases for assignment/consent requirements | Q. Sarr | Medium | Open | 2024-05-04 | 2024-05-20 | Two leases identified; landlord consent language under review
8 | Litigation | Confirm status of pending vendor dispute disclosed in data room | M. Feld | Medium | Open | 2024-05-05 | 2024-05-19 | Awaiting litigation summary from target counsel
9 | Regulatory | Confirm target's permits/licenses transfer with change of control | R. Okafor | Medium | Open | 2024-05-06 | 2024-05-20 | State-level licensing review in progress
10 | MIP Mechanics | Reconcile management incentive plan pool calculation against latest cap table | Q. Sarr | High | In Progress | 2024-05-07 | 2024-05-14 | Whitfield/Sandhurst MIP mechanics receipt confirmed per I. Solheim and deal status meeting on 2024-05-14; prior cap table version was stale. Reconciliation proceeding against confirmed MIP mechanics; still awaiting updated fully diluted cap table (see Item #1) to complete final calculation. Whitfield Estoppel Escalation working session confirmed Whitfield Counterparty Counsel has still not responded to the cap table request, so this item remains blocked pending Item #1. Due date has passed; re-escalation initiated at working session and now being tracked via Item #1's extended due date
11 | Integration | Confirm data privacy/security policies compatible with Northmoor standards | L. Barsanti | Low | Open | 2024-05-07 | 2024-05-22 | Initial policy comparison scheduled
12 | Corporate | Confirm no undisclosed related-party transactions | Q. Sarr | Medium | Open | 2024-05-08 | 2024-05-21 | Related-party questionnaire sent to target CFO
13 | Closing Logistics | Finalize and confirm delivery of estoppel deadline letter | Q. Sarr | High | Closed | 2024-05-09 | 2024-05-10 | Letter finalized and confirmed sent per I. Solheim; deadline tracked, no further action required
14 | Corporate Housekeeping | Confirm good standing certificates for target entities | Q. Sarr | Medium | Closed | 2024-05-09 | 2024-05-10 | 12 of 12 entities confirmed in good standing per D. Reinhardt