## Diligence & Closing Items
Item | Category | Status | Owner | Due Date | Notes
DE good standing certificates (12 entities) | Corporate Diligence | Complete | Quentin Sarr | 2025-05-20 | 12/12 confirmed
Odell estoppel certificate | Real Property | Outstanding | Quentin Sarr | 2025-05-27 | Escalated to counterparty counsel; Quentin flagged for MP-level escalation
Whitfield estoppel certificate | Real Property | Outstanding | Quentin Sarr | 2025-05-27 | Escalated to counterparty counsel; Quentin flagged for MP-level escalation
Reconciliation of diligence tracker vs. data room index | QC / Reconciliation | In Progress | Ulrich Bergmann | 2025-05-23 | Bennett Ashworth reconciled on his end; Desmond confirmation pending
Staffing confirmation for Sandhurst matter | Deal Staffing | Complete | Saoirse Mulvaney | 2025-05-22 | MP staffing call held; outcome confirmed with Saoirse Mulvaney
MP availability for client call | Client Relationship | Complete | Dov Reinhardt | 2025-05-22 | 15-min call with managing partner held per Saoirse Mulvaney's request
MIP mechanics fix - Sandhurst platform deal | Deal Structuring | Escalated - Urgent | Dov Reinhardt | 2025-05-21 | Third escalation on this issue; must be resolved today
Purchase agreement - representations & warranties markup | Definitive Agreements | In Progress | Dov Reinhardt | 2025-05-26
Disclosure schedules - property section | Definitive Agreements | Blocked | Quentin Sarr | 2025-05-28 | Depends on outstanding estoppels
Financing commitment letter review | Financing | Not Started | Dov Reinhardt | 2025-05-29
Closing set assembly | Closing Mechanics | Not Started | Dov Reinhardt | 2025-05-30