## Closing Checklist
Item | Category | Responsible Party | Status | Due Date | Notes
Delaware good standing certificate - Target | Corporate Formalities | Quentin Sarr | Complete | 2025-06-10 | 12/12 entities confirmed good standing in DE
Odell Fabrication, LLC - landlord estoppel certificate | Real Property | Quentin Sarr | Outstanding | 2025-06-17 | Follow-up sent to landlord counsel; response still pending as of deal status meeting
Whitfield Logistics Center - landlord estoppel certificate | Real Property | Quentin Sarr | In Progress | 2025-06-17 | Call held directly with Whitfield's counsel per Dov's outreach; landlord counsel now engaged - awaiting revised estoppel draft
UCC lien searches - all target entities | Secured Financing | Quentin Sarr | Complete | 2025-06-05 | No unreleased liens found
Material contracts - change of control review | Contracts | Quentin Sarr | Complete | 2025-06-08 | No consents required except Odell/Whitfield leases
Officer and director resignation letters | Corporate Formalities | Quentin Sarr | In Progress | 2025-06-20 | Drafts circulated to target counsel
Payoff letters - existing credit facility | Financing | Quentin Sarr | In Progress | 2025-06-18 | Updated payoff figures requested again from lender following deal status meeting; no figures received yet
D&O tail insurance binder | Insurance | Quentin Sarr | In Progress | 2025-06-22 | Carrier identified; awaiting premium quote from broker
Employment agreements - key employees | HR/Employment | Quentin Sarr | Complete | 2025-06-12 | All signed, no outstanding issues
Closing set index and signature pages | Closing Logistics | Quentin Sarr | In Progress | 2025-06-19 | Coordinating with all parties on execution