## Closing Checklist
Item # | Task | Responsible Party | Status | Due Date | Notes
1 | Confirm final target entity structure (Sandhurst Holdings LLC and subsidiaries) | M. Chandrasekhar | In Progress | 2025-05-30 | Updated org chart received from Sandhurst counsel; final confirmation pending internal review. REVIEW NOTE (Q. Sarr): Org chart on file supports this - sign off once internal review closes.
2 | Complete corporate diligence review - charter docs, bylaws, good standing certificates | M. Chandrasekhar | In Progress | 2025-06-02 | Delaware and Ohio entities confirmed; Seller (PA entity) good standing certificate is the sole outstanding item of 12 - still awaited, unlikely to arrive today; will flag immediately upon receipt. REVIEW NOTE (Q. Sarr): Evidence thin until PA certificate is in hand - do not represent this item as complete in any closing memo or client update until received; flag to M. Odell if it slips past 6/2. UPDATE: Per S. Bhatt, good standing now confirmed 11 of 12 - one certificate (consistent with PA entity) still outstanding; status and note above remain accurate, do not advance to complete. REVIEW NOTE (Q. Sarr, follow-up): 11-of-12 figure is now adequately evidenced via S. Bhatt's update - sign off on that count, but the item as a whole still cannot be marked complete until the final PA certificate is received; do not advance status. REVIEW NOTE (Q. Sarr, latest): 12/12 good standing was reported at today's deal status meeting, implying the PA certificate has now come in - but I do not yet have the certificate itself or a written confirmation from S. Bhatt on file, only the verbal report. Evidence is thin for closing this item on that basis alone; hold status at 'In Progress' until the certificate is actually received and the record updated accordingly, then advance to Complete. REVIEW NOTE (Q. Sarr, meeting follow-up): Today's corporate deal status meeting confirmed the Sandhurst checklist figure at 11/12, not 12/12, and separately flagged the OH entity's good standing as a point needing attention - this is consistent with the 11-of-12 count already on file and does not evidence receipt of the outstanding PA certificate. Sign off on the 11/12 figure as corroborated; status remains 'In Progress' pending actual receipt of the final certificate and written confirmation from S. Bhatt.
3 | Review material contracts for change-of-control provisions | M. Chandrasekhar | Not Started | 2025-06-05 | Flagged 3 customer contracts with consent requirements in prior pass. REVIEW NOTE (Q. Sarr): Prior-pass flag is a reasonable basis to proceed on schedule - no objection, sign off on approach.
4 | Finalize disclosure schedule cross-references to purchase agreement | M. Chandrasekhar | In Progress | 2025-06-04 | Coordinating with Q. Sarr on numbering conventions. REVIEW NOTE (Q. Sarr): Confirmed coordination is active on my end - sign off, no concerns.
5 | Confirm UCC lien search results and payoff letters | S. Bhatt | In Progress | 2025-06-03 | Two liens identified; payoff letters requested from lenders, still awaited. REVIEW NOTE (Q. Sarr): Per S. Bhatt, checklist unchanged as of today's chat - status should not be advanced past 'In Progress' until payoff letters are actually in hand; evidence currently supports request only, not resolution. REVIEW NOTE (Q. Sarr, follow-up): No new evidence since last check - flag stands, do not advance until payoff letters are confirmed received.
6 | Draft and circulate closing set index | S. Bhatt | Not Started | 2025-06-06 | Template based on prior Northmoor add-on. REVIEW NOTE (Q. Sarr): Reasonable template basis - sign off, no changes needed at this stage.
7 | Obtain signature pages from all Sandhurst equityholders | Q. Sarr | Not Started | 2025-06-10 | 12 equityholders total; 4 confirmed availability for signing. REVIEW NOTE (Q. Sarr): Own item - flagging for myself that 8 of 12 remain unconfirmed with due date approaching; need to push outreach before this can move to In Progress. REVIEW NOTE (Q. Sarr, follow-up): No change in confirmed count since last note - flag stands, outreach still required before status can move.
8 | Confirm regulatory/antitrust filing status (if applicable) | Q. Sarr | Not Started | 2025-06-01 | Size of transaction likely below HSR threshold - confirm with M. Odell. REVIEW NOTE (Q. Sarr): Own item - 'likely below threshold' is not yet confirmed; due date has passed (6/1) without confirmation from Odell. Do not treat as resolved - needs immediate follow-up. REVIEW NOTE (Q. Sarr, follow-up): Still no confirmation from Odell as of this review - flag remains open and overdue; escalate if unresolved by next check-in.
9 | Review employment agreements for key Sandhurst management | M. Chandrasekhar | Not Started | 2025-06-07 | Retention agreements for 3 key executives still being negotiated. REVIEW NOTE (Q. Sarr): Evidence thin - negotiations ongoing means this task cannot be scoped as final review yet; recommend keeping at Not Started until terms settle rather than advancing prematurely.
10 | Confirm insurance policy assignment/tail coverage arrangements | S. Bhatt | Not Started | 2025-06-08 | REVIEW NOTE (Q. Sarr): No notes or supporting detail on file for this item - evidence is entirely absent, not merely thin. Cannot sign off; requesting S. Bhatt provide status detail before this can be assessed. REVIEW NOTE (Q. Sarr, follow-up): Still no supporting detail provided as of this review - request to S. Bhatt remains outstanding. REVIEW NOTE (Q. Sarr, latest): Per chat with Dov Reinhardt, Samir has now confirmed this item closed - sign off on closure; status should be updated to Complete once S. Bhatt formally updates the record, but evidence now supports resolution rather than an open request.
11 | Finalize escrow agreement terms with escrow agent | Q. Sarr | In Progress | 2025-06-05 | Draft circulated to S. Whitfield for comment; awaiting Odell/Whitfield response. REVIEW NOTE (Q. Sarr): Own item - per Ingrid's check-in, no response yet from either Odell or Whitfield; status of 'In Progress' reflects circulation only, not substantive progress. Will escalate if no reply by tomorrow. REVIEW NOTE (Q. Sarr, follow-up): Per chat with I. Solheim, this item has now been escalated on the Whitfield/Sandhurst front - escalation only, not a substantive response; status remains 'In Progress' reflecting circulation and escalation, not resolution.
12 | Prepare closing memo for client (M. Odell) | M. Chandrasekhar | Not Started | 2025-06-11 | To follow execution of purchase agreement. REVIEW NOTE (Q. Sarr): Sequencing is sound - sign off, dependent on purchase agreement execution as noted.
13 | Confirm wire instructions and funds flow memo | S. Bhatt | Not Started | 2025-06-11 | REVIEW NOTE (Q. Sarr): No supporting detail on file - cannot assess or sign off until status notes are added by S. Bhatt. REVIEW NOTE (Q. Sarr, follow-up): Still no detail provided as of this review - request remains open.
14 | Post-closing deliverables checklist (recorded assignments, filings) | M. Chandrasekhar | Not Started | 2025-06-13 | To be finalized after closing date confirmed. REVIEW NOTE (Q. Sarr): Sign off - appropriately deferred pending closing date.
15 | Resolve outstanding tenant estoppel certificates | Q. Sarr | In Progress | 2025-06-09 | Confirmed 2 of 3 estoppels still outstanding (count reconciled with Samir after brief discrepancy); Odell/Whitfield outreach ongoing by Q. Sarr, no callback yet. REVIEW NOTE (Q. Sarr): Own item - count now reconciled with M. Chandrasekhar per her confirmation, so the '2 of 3' figure is solid. Still awaiting callback; will re-flag if no response by due date. SEPARATE ITEM (Q. Sarr): Mira's Secretary's Certificate query is distinct from the estoppel count above - initially unchecked, now confirmed closed per Ingrid's update; no impact on estoppel status. FOLLOW-UP (Q. Sarr): Per Ingrid's Articles 4-7 close-out message, this resolution is corroborated - no change to '2 of 3' outstanding figure or In Progress status; will advance only upon actual callback. LATEST (Q. Sarr): Per chat with S. Whitfield, matter has now been escalated on the estoppel front; this is an escalation only, not a resolution - evidence still does not support advancing beyond 'In Progress' or reducing the '2 of 3' outstanding figure until actual estoppel certificates are received. Will update again once escalation yields a substantive response. REVIEW NOTE (Q. Sarr, follow-up): Per I. Solheim's status-quo message and subsequent cross-check exchange, no substantive change to report - '2 of 3' outstanding and escalation-only status both stand; do not advance until certificates are actually received.