## Closing Checklist
Item # | Deliverable | Responsible Party | Status | Received/Executed Date | Notes | Reviewer Notes (GP)
1 | Stock Purchase Agreement - execution version | Northmoor Counsel | Complete | 2025-05-12 | Fully executed, all signature pages collected | Signed off - execution confirmed, no further action.
2 | Disclosure Schedules - final | Sandhurst Counsel | Complete | 2025-05-11 | Reconciled against SPA reps | Signed off - reconciliation noted, adequate support.
3 | Escrow Agreement | Escrow Agent Counsel | Complete | 2025-05-12 | Signed by all three parties | Signed off - fully executed.
4 | Payoff Letters - senior lender | Sandhurst Finance | Complete | 2025-05-09 | Wire instructions confirmed | Signed off.
5 | UCC Termination Statements | Samir Bhatt | Complete | 2025-05-10 | Filed with Secretary of State, confirmation received | Signed off - filing confirmation is sufficient evidence.
6 | Good Standing Certificates - all entities | Samir Bhatt | Complete | 2025-05-14 | 12 of 12 confirmed as of EOD - Sandhurst Real Estate Holdco, LLC (Delaware, Whitfield property) certificate received, closing the prior outstanding gap. Entity Chart Snapshot updated accordingly. Ardmore Elevator good standing certificate content separately reviewed and cleared for closing binder filing - distinct workstream, now complete. | REVIEW NOTE - STILL OPEN, re-reviewed again today, no change since my last note and no new evidence received. 'Confirmed' relies on Samir's tracker entry; the Real Estate Holdco certificate itself has still not been sent to me, and nothing has come in overnight or since. The Notes column's characterization of this line as fully closed is the tracker's conclusion, not one I've independently verified - I am not signing off on 12-of-12 closure until the certificate is in my file. Ardmore Elevator clearance separately noted but same caveat applies - I want the reviewed content, not just confirmation it was reviewed. Please send the certificate directly rather than waiting for the next periodic update.
7 | Officer's Certificates | Sandhurst Management | In progress |  | 3 of 4 back - four required signatories confirmed as CEO, CFO, and the officers of Sandhurst Operating Co. and Sandhurst Add-On 1; outstanding certificate is for the officer of Sandhurst Real Estate Holdco, LLC. Good standing for that entity is now closed (item 6); officer's certificate remains the last open item on this line. | Confirmed - missing signatory identified by name/role, that part is well-supported and stands. But the Notes column's premise that 'good standing for that entity is now closed' is not something I can adopt - see item 6, where I still have not seen the certificate. Tracking continues on officer's certificate alone; I'm not treating the good-standing dependency as resolved for review purposes. Re-reviewed again today, no change.
8 | Secretary's Certificates w/ Charter Docs | Samir Bhatt | Complete | 2025-05-13 | 4 of 4 back | Signed off - complete set confirmed.
9 | Non-Compete / Restrictive Covenant Agreements (Add-On Targets) | Northmoor Counsel | Outstanding |  | Awaiting execution by two add-on principals. Northmoor Counsel confirmed both principals have agreed to terms; execution scheduled within 2 business days of this update. | REVIEW NOTE - STILL OPEN, re-reviewed again today, no change since my last note. Agreement to terms and a scheduled date are not execution; no signature pages have been reported received. Keep this outstanding until signature pages are actually received; please don't let the 'firm date' soften the status in the next update.
10 | Employment Agreements - key employees | Sandhurst HR Counsel | Outstanding |  | Awaiting redline resolution - open issue is scope of post-employment non-solicit provision (duration and geographic scope) for two key employees; all other terms agreed. | Noted - the open issue is specific enough to track meaningfully, and that stands. Continue tracking as outstanding pending resolution of non-solicit scope; flag for me if geographic scope becomes contested, that's the piece likely to need my input.
11 | Lien Search Results - final refresh | Samir Bhatt | Complete | 2025-05-08 | No liens outside those being terminated | Signed off - clean search, consistent with UCC terminations at item 5.
12 | Litigation Search Results | Samir Bhatt | Complete | 2025-05-08 | Clean across all target entities | Signed off.
13 | Consents - material contracts | Sandhurst Counsel | In progress |  | 13 of 14 back - outstanding counterparty confirmed as a regional equipment lessor (non-material, not a closing condition per SPA Section 5.2 schedule of required consents). | REVIEW NOTE - STILL OPEN, re-reviewed again today, no change since my last note. Before I sign off on 'non-material,' I want to see the SPA Section 5.2 schedule myself to confirm this lessor isn't listed as a required consent; that schedule still has not been sent to me. Likely fine, but I'd rather confirm against the schedule than rely on the characterization alone.
14 | Consents - landlord estoppels | Sandhurst Counsel | In progress |  | 1 of 3 back - outstanding estoppels are for the Odell and Whitfield properties, both closing conditions. Whitfield workstream escalated: a deadline letter has been drafted and sent to Whitfield's counsel, replacing the prior registered-agent follow-up as the current next action; EOD monitoring in place for a response. Estoppel certificates and MIP mechanics receipt confirmation for Whitfield remain items for Quentin/Dov to own and report, not Samir - Samir has no holder ID for the estoppel/supplier file and this is not his item to chase. Samir retains ownership of the overall closing checklist and will update this line upon Quentin's or Dov's report. | Escalated as its own line item per prior reviewer instruction - do not fold back into general 'in progress' status; that stands. Deadline letter escalation noted; status remains open pending Whitfield counsel response and Odell update, with reporting ownership confirmed as Quentin/Dov's, not Samir's. REVIEW NOTE - STILL OPEN, re-reviewed again today, no change since my last note. No response from Whitfield counsel has been reported to me; please loop me in directly the moment it arrives. This remains the widest closing-condition gap on the checklist and I don't want it surfacing only through the next periodic update.
15 | D&O Tail Insurance Binder | Sandhurst Insurance Broker | Complete | 2025-05-11 | Six-year tail confirmed | Signed off - term confirmed adequate.
16 | Closing Set - assembly and distribution | Samir Bhatt | Not started |  | Gated on items 7, 9, 10, 13, 14. Item 6 (good standing) is now fully closed at 12 of 12 and no longer a gating item; Ardmore Elevator cleared separately for closing binder filing. Item 7 gap now narrowed to the Real Estate Holdco officer's certificate alone. Items 9 and 10 remain fully outstanding pending execution and redline resolution, respectively. Item 14 remains the widest gap (1 of 3, two closing-condition estoppels open), with Whitfield escalated via deadline letter and Odell/Whitfield ownership confirmed as Quentin/Dov's. Countdown to assembly not yet started. | REVIEW NOTE - STILL OPEN, re-reviewed again today, consistent with my notes above and unchanged since last review. I don't accept the Notes column's premise that item 6 is 'fully closed... and no longer a gating item' until I've seen the certificate referenced at item 6/7. As stated: the gating list is properly 7, 9, 10, 14, and within 7 the remaining piece is tied to the same unverified certificate. Otherwise this note accurately reflects the remaining gates.
17 | Add-On Diligence Memo - open items summary | Northmoor Counsel | In progress |  | Draft circulated for comment | Noted status as stated - I have not reviewed the draft's substance and take no position on it; no action needed from me until comments come back, at which point flag for follow-up.

## Entity Chart Snapshot
Entity | Jurisdiction | Status Check | Good Standing Received | Reviewer Notes (GP)
Sandhurst Platform Holdings, Inc. | Delaware | Confirmed active | Yes | Signed off.
Sandhurst Operating Co., LLC | Delaware | Confirmed active | Yes | Signed off.
Sandhurst Add-On 1, LLC | Texas | Confirmed active | Yes | Signed off.
Sandhurst Add-On 2, LLC | Texas | Confirmed active | Yes | Signed off - certificate received, no longer the outstanding entity.
Sandhurst Real Estate Holdco, LLC | Delaware | Confirmed active | Yes | REVIEW NOTE - STILL OPEN, re-reviewed again today, no change since my last note. 'Yes' here is marked on the strength of the checklist entry at item 6, but I have not personally reviewed the certificate and it has not been sent to me. Please send it over; I'll sign off on this row and close out items 6/7 together once I have.
Northmoor Acquisition Sub, Inc. | Delaware | Confirmed active | Yes | Signed off.