## Closing Checklist
Item # | Workstream | Task | Responsible Party | Status | Due Date | Notes
1 | Corporate | Confirm target good standing certificates (all jurisdictions) | Quentin Sarr | In Progress | TBD | Sandhurst secretary of state responses partially received; following up on remaining jurisdictions per deal status meeting
2 | Corporate | Review and finalize disclosure schedules | Quentin Sarr | In Progress | TBD | Coordinating with Northmoor deal team; targeting finalization following resolution of White Oak consent
3 | Contracts | Complete material contract review and change-of-control flags | Samir Bhatt | In Progress | TBD | Escalation to outside counsel pending on White Oak lease consent
4 | Contracts | Obtain third-party consents identified in diligence | Samir Bhatt | Open | TBD | White Oak consent outstanding - escalated to outside counsel; status confirmed at deal status meeting
5 | Real Estate | Confirm leasehold estoppels for all leased facilities | Quentin Sarr | Open | TBD
6 | Employment | Review key employee agreements and retention arrangements | Mira Chandrasekhar | In Progress | TBD
7 | IP | Confirm IP assignment agreements are complete and recorded | Quentin Sarr | Not Started | TBD
8 | Regulatory | Confirm no outstanding regulatory approvals required | Mira Chandrasekhar | In Progress | TBD
9 | Finance | Confirm payoff letters for existing indebtedness | Samir Bhatt | Not Started | TBD
10 | Closing Mechanics | Prepare closing set / signature pages checklist | Quentin Sarr | Not Started | TBD | To begin once disclosure schedules finalized
11 | Closing Mechanics | Circulate closing checklist to all workstream leads | Quentin Sarr | Done | Complete | v3 update circulated following deal status meeting
12 | Add-on Diligence | Coordinate Sandhurst add-on diligence findings into main file | Quentin Sarr | In Progress | TBD | See tkt-000011 workstream; discussed at deal status meeting, awaiting confirmation no further consents outstanding
13 | Add-on Diligence | Confirm no further Sandhurst consents outstanding beyond those already identified | Mira Chandrasekhar | Open | TBD | Raised at deal status meeting; Quentin Sarr to push explicitly for confirmation from Sandhurst counsel

## Open Escalations
Issue | Raised By | Escalated To | Status | Notes
White Oak lease consent - change of control | Quentin Sarr | Outside Counsel | Escalated | Escalation sent per chat thread with Mira Chandrasekhar and Samir Bhatt; status reaffirmed at Corporate deal status meeting
Confirmation of no further Sandhurst consents outstanding | Mira Chandrasekhar | Samir Bhatt / Quentin Sarr | Awaiting Response | Following up after deal status meeting; Quentin Sarr to press outside counsel/Sandhurst for written confirmation