## Filing Status
Application / Matter | Filing Type | Docket Deadline | Status Bucket | Current Status | Days to Deadline | Notes
Control-Loop Feedback Mechanism — US Priority | Non-Provisional | 2025-06-27 | Filed | Filed with USPTO; confirmation number received | 0 | On track; matched against docketing calendar, no discrepancy found
Control-Loop Feedback Mechanism — Continuation Claims (Sensor Fusion) | Continuation | 2025-07-15 | In Draft | Claims drafted, awaiting inventor review | 18 | Distinct from priority filing; not yet filed, drafting stage confirmed with Klara
Control-Loop Feedback Mechanism — PCT | PCT (International) | 2025-06-27 | Filed | PCT application filed same day as US priority | 0 | On track
Control-Loop Adaptive Gain Adjustment — Divisional | Divisional | 2025-08-01 | In Draft | Specification drafted; claims not finalized | 35 | No blocking issue identified; monitor for chain-of-access resolution before finalizing inventorship
Control-Loop Feedback Mechanism — EP Regional Phase | Regional Phase Entry | 2026-01-15 | At Risk | Entry not yet initiated; dependent on PCT search report | 233 | Not urgent yet but flagged as at-risk pending foreign filing license confirmation
Departing Engineer — Inventorship Chain-of-Access Review | Related Matter (non-filing) |  | At Risk | Chain-of-access to lab notebooks/design files not yet confirmed for departing engineer |  | Non-blocking for current deadline per Priyanka thread; being checked separately, flagged here for visibility only
Cease & Desist — Competing Control-Loop Implementation | Related Matter (non-filing) |  | At Risk | C&D sent, no response received |  | Tracked separately from patent filing set; included per Klara's question for context

## Summary
Bucket | Count | Comment
Filed | 2 | US priority and PCT both filed on schedule; verified against docketing calendar
In Draft | 2 | Continuation and divisional in progress; no docket deadline currently at risk
At Risk | 3 | EP regional phase entry timing dependency; departing-engineer chain-of-access; C&D non-response — none currently blocking the confirmed control-loop deadline