## Variance Summary
Line Item | Approved Budget ($) | Actual/Projected ($) | Variance ($) | Variance (%) | Driver | Support Reference
Reserve Analysis & Board Exposure Memo (Sections I, VI, VII, VIII) | 45000 | 58500 |  |  | Finalized reserve figure reconciled against board exposure quantitative support schedule; additional reconciliation cycles required | doc-000333; doc-000346
WIP and Realization Report — Cycle Close (Sandhurst status resolution) | 12000 | 15800 |  |  | Sandhurst time-status question required additional review before cycle close could be finalized | doc-000348
Ardmore — Enforcement Inquiry / Chain-of-Access Follow-Up | 8000 | 13250 |  |  | Repeated owner-unresponsive escalations (Samir) required four follow-ups through Gideon before substantive response; discrete follow-up item remains open | doc-000348
Pryor Deposition Summary — Redline and Citation Pass | 9500 | 16200 |  |  | Heavy redline pass tightening characterizations to record-anchored statements and correcting citation placeholders; flagged admission and impeachment inconsistency required senior partner review time beyond original scope | doc-000344
Second Request for Production — Response, Scope, and Objections | 22000 | 27600 |  |  | Deadline clarification (14 days from issuance), meet-and-confer sequencing analysis, and covenant-amendment-overlap review | Response to Second Request for Production memo; covenant-amendment-analysis memo
Cotswold Committee Memo — Sign-Off Coordination | 4000 | 5100 |  |  | Escalation coordination on sign-off delay; Lucien assigned with end-of-day escalation path | internal correspondence — Rosalie chase
Deshmukh / Ardmore Closure — Documentation and Sweep List Update | 3500 | 5900 |  |  | Closure documentation for good-standing filing and chain-of-access routing, logged as two separate lines both closed 12/12 | doc-000348 Sweep List
TOTAL

## Variance Detail — Ardmore & WIP
Date | Item | Status | Owner | Hours Variance | Notes
12/12 | Ardmore — Good Standing Filing | Closed | Bennett Ashworth | 3.5 | Logged as separate line from chain-of-access routing per confirmed instruction; same closure date, distinct matter
12/12 | Ardmore — Chain-of-Access Routing | Closed | Samir | 6.2 | Separate matter from good-standing filing; closed same date; residual follow-up flagged as discrete open task, not blocking closure
Ongoing | Sandhurst Time-Status Question | Resolved — No Outstanding Items | Samir (confirmed) | 4.8 | Cleared WIP/Realization Report as final for cycle close per confirmed inputs
Ongoing | Reserve Figure Reconciliation | Finalized | Bennett Ashworth / Samir | 9 | Reconciled against doc-000346 board exposure quantitative support schedule

## Panel Compliance Q&A Support
Question Raised by Panel | Response | Support Document(s)
Why does professional liability matter show a variance above approved budget? | Variance driven by five discrete items: reserve reconciliation finalization, WIP/realization cycle-close resolution, Ardmore escalation cycle, deposition-summary redline pass, and Second Request scope/objection analysis. See Variance Summary tab for itemized dollar and percentage detail by line. | doc-000333; doc-000346; doc-000344; doc-000348
Has the reserve figure changed as a result of these overages? | No. Reconciliation confirms no change to liability, damages, or coverage posture; overage reflects time to finalize and reconcile the existing figure, not a change in the figure itself. | doc-000333; doc-000346
Is the Ardmore item still open and driving further overage risk? | Chain-of-access follow-up remains a discrete open item under Samir's ownership; good-standing filing is closed. Reassignment of ownership was threatened if no response was received; monitor next cycle for further variance. | doc-000348
Does the Second Request overage reflect scope creep? | No additional scope was undertaken; overage reflects deadline clarification (14 days, not three weeks) and confirmation that meet-and-confer window is already built into the production schedule, plus confirmation of no covenant-amendment overlap requiring review. | Response to Second Request for Production memo