# Pryor Reply Brief – Work Plan & Staffing Outline

Prepared by Hyun-woo Bae. Filing deadline: one week from Monday. This outline sets the workstreams, sequencing, and staffing needed to file a complete, cite-checked reply on time, with buffer for partner review and final QC before service.

## 1. Governing deadline and internal milestones

Court deadline: reply brief due one week from Monday (the following Monday). Treat this as immovable.

Internal draft-complete target: Wednesday of the deadline week, to leave two clear days for partner review and revision.

Cite-check and record-cite verification lock: Thursday EOD.

Final proofread and table of authorities/exhibits check: Friday.

Filing-ready PDF assembled and circulated for sign-off: Friday EOD.

Filed and served: Monday morning, ahead of the court's stated cutoff.

## 2. Workstreams

Substantive argument drafting — responds point-by-point to opposition's brief; owns the legal argument sections.

Record and deposition support — pulls and verifies citations to the Pryor deposition summary and record evidence; confirms no timeline discrepancies (already reviewed, no issues found on the timeline section).

Cite-check and Bluebook/local-rule compliance — verifies every citation, pin cite, and quotation against source documents.

Exhibit and appendix assembly — compiles supporting exhibits, declarations, and appendix in filing order.

Partner review and revision — substantive read for argument strength, tone, and risk; sets revision priorities.

Final production and filing — formats to court rules, converts to PDF, files and serves.

## 3. Staffing outline

| Workstream | Lead | Support | Target completion |
| --- | --- | --- | --- |
| Substantive argument drafting | Partner (assign on kickoff) | Hyun-woo Bae | Wed, deadline week |
| Record/deposition support | Hyun-woo Bae | — | Complete — no open issues |
| Cite-check & compliance | Rosalie | Hyun-woo Bae (spot-check) | Thu EOD, deadline week |
| Exhibit/appendix assembly | Rosalie | Hyun-woo Bae | Thu EOD, deadline week |
| Partner review & revision | Partner (assign on kickoff) | Hyun-woo Bae | Fri, deadline week |
| Final production & filing | Hyun-woo Bae | Rosalie | Mon AM, filing day |

## 4. Status inputs already in hand

Pryor deposition summary and reply-status memo reviewed; timeline section confirmed with no issues.

Rosalie is available for cite-check and exhibit-list work — she was cleared off Sable Ridge exhibit build once that filing went out, and her privilege log and cite-check/declaration package experience there (including closing out Ex. 17) transfers directly to this exhibit assembly workstream.

## 5. Risks and open items

Partner assignment for substantive drafting lead is not yet confirmed — needed by kickoff to hold the Wednesday draft-complete target.

No slack remaining in the schedule if court rules require unusual formatting (e.g., word-count certification, local exhibit tabbing) — to be confirmed at kickoff.

Will flag promptly if any workstream slips past its internal milestone, rather than waiting for the Friday checkpoint.