## Master Docket
Matter | Deadline Description | Governing Rule/Order | Owner | Due Date | Days Remaining | Status | Notes
Sable Ridge - Driver Meal-Break Collective Action | Opposition to Conditional Certification Motion due | Case Management Order, Dkt. 44 | Litigation Team - lead TBD | 2025-06-20 |  | Open | Confirm assigned associate; draft not yet started per last status check
Sable Ridge - Driver Meal-Break Collective Action | Expert disclosure deadline (Plaintiff) | FRCP 26(a)(2) / Scheduling Order | Litigation Team | 2025-07-11 |  | Open | Awaiting plaintiff service; confirm receipt when due
Sable Ridge - Driver Meal-Break Collective Action | Expert disclosure deadline (Defendant) | FRCP 26(a)(2) / Scheduling Order | Litigation Team | 2025-08-08 |  | Open | Retain expert; confirm engagement letter executed
Sable Ridge - Driver Meal-Break Collective Action | Close of fact discovery | Scheduling Order | Litigation Team | 2025-09-05 |  | Open | Track outstanding written discovery and depositions
Sable Ridge - Driver Meal-Break Collective Action | Dispositive motion deadline | Scheduling Order | Litigation Team | 2025-10-17 |  | Open
Coastal Meridian - Regulatory Inquiry | Response to regulator information request due | Agency letter dated per file | Regulatory Team | 2025-06-13 |  | Open | Confirm extension request status if any
Coastal Meridian - Credit Agreement Covenant Review | Covenant compliance certificate delivery | Credit Agreement Sec. 7.1 | Finance/Corporate Team | 2025-06-30 |  | Open | Coordinate with client finance team on figures
Halden Orthopedics - Renwick Non-Compete | Response to TRO opposition due | Court order | Litigation Team | 2025-06-11 |  | Open | High priority - confirm draft circulated for review
Halden Orthopedics - Tessaro Malpractice Defence | Answer to Second Amended Complaint due | FRCP 15 / Court order | Litigation Team | 2025-06-25 |  | Open
Verity Grain - Ardmore Elevator Acquisition | Target closing date | Purchase Agreement Sec. 9 | Corporate Team | 2025-07-01 |  | Open | Confirm closing checklist on track
Verity Grain - Hollstead Supply Dispute | Demand letter response deadline | Contract notice provision | Litigation Team | 2025-06-16 |  | Open
Pellumbra - Ravenna Collaboration Agreement | Exclusivity period expiration | Term Sheet Sec. 4 | Corporate Team | 2025-07-15 |  | Open
Pellumbra - Series C Disclosure Schedule | Disclosure schedule delivery to investor counsel | Stock Purchase Agreement draft | Corporate Team | 2025-06-18 |  | Open | Confirm all business units have submitted updates
Pellumbra - Cross-Border Clinical Data Assessment | Regulatory filing deadline (data transfer notice) | Applicable data protection statute | Regulatory Team | 2025-06-27 |  | Open
Northmoor - Sandhurst Platform Acquisition | Financing commitment expiration | Commitment Letter | Corporate Team | 2025-07-05 |  | Open
Northmoor - Sandhurst Add-On Diligence | Whitfield estoppel certificate follow-up - escalated to Quentin (outside counsel) | Purchase Agreement diligence condition | Quentin (outside counsel) - follow-up pending | 2025-06-12 |  | Escalated - awaiting response | Second reminder sent; no response yet from Quentin as of last check
Formulas:
Days Remaining = [Due Date]-TODAY()