## Master Docket
Deadline | Days Remaining | Event / Filing | Governing Rule / Order | Owner | Status | Notes
2024-06-03 | 5 | Opposition to Conditional Certification Motion due | Scheduling Order dated 2024-03-15, Dkt. 42 | Fionnuala Doherty | In progress | Draft circulated for review 2024-05-28; awaiting declarations from ops team
2024-06-10 | 12 | Deadline to serve supplemental discovery responses (meal-break policy docs) | FRCP 34(b)(2); Joint Stipulation Dkt. 51 | Adaora Nwosu | Not started | Client IT pulling timekeeping exports; confirm production format with opposing counsel
2024-06-17 | 19 | Deadline to file Notice re: Proposed Notice to Putative Class | Court Order Dkt. 47 ¶3 | Fionnuala Doherty | Not started | Contingent on outcome of conditional certification briefing
2024-06-21 | 23 | Expert disclosure deadline (liability) | Rule 26(a)(2) Scheduling Order Dkt. 42 | Adaora Nwosu | Not started | Confirm retained expert availability by 2024-06-07
2024-07-01 | 33 | Deadline to respond to Plaintiffs' Motion to Compel | Local Rule 37.1 | Fionnuala Doherty | Not started | Meet-and-confer held 2024-05-30; response only needed if unresolved
2024-07-15 | 47 | Close of opt-in period (if certification granted) | Anticipated per Order Dkt. 47 | Adaora Nwosu | Contingent | Clock starts on date notice is mailed, not on this date; recalendar upon certification ruling
2024-08-05 | 68 | Fact discovery cutoff | Scheduling Order Dkt. 42 | Fionnuala Doherty | Not started | Reassess after opt-in period closes; may need extension motion