## Slide 1: Sandhurst Platform Acquisition — Closing Status
End-of-day status update prepared for tomorrow's board readout
Covers: estoppel escalation tracker, good standing certificate, ancillary documentation/staffing split
Confirmed EOD: closing checklist and diligence tracker are reconciled and tie out — no discrepancies remain
Notes: Framing slide. Emphasize this is a consolidated snapshot as of EOD; two items remain open heading into the board call. Closing checklist status report and diligence tracker have been reconciled and confirmed to tie out.

## Slide 2: Whitfield/Odell Estoppel — Escalated to Counsel, Still Open
No change in resolution: Whitfield and Odell estoppel certificates (2 of 3) remain outstanding
Item has been escalated to counsel; no callback or response received yet as of EOD
Escalation note on file (Escalation Note — Odell/Whitfield Estoppel Certificate) documents outreach and escalation history
Prior reporting discrepancy (Samir's '1 of 3 open' figure) has been fully reconciled — 2 of 3 open is the confirmed, current count
Ownership of the Whitfield/Odell escalation follow-up sits with the team pending counsel response
Notes: Flag the escalation status clearly for the board: this has moved beyond routine outreach to counsel-level escalation with no response yet. Closing checklist and diligence tracker both reflect this consistently. No further movement since escalation.

## Slide 3: Good Standing Certificate — Last Outstanding Item
Delaware good standing certificate for Seller (Sandhurst Real Estate Holdco LLC, Whitfield jurisdiction) is the last outstanding good-standing item
Secretary's Certificate item is now closed and no longer tracked as open
Checklist otherwise clean apart from this single remaining jurisdiction
Will flag to the team immediately upon receipt
Notes: Consistent with the reconciled closing checklist: only the Whitfield/Sandhurst Real Estate Holdco LLC good standing certificate remains outstanding. Do not overstate likelihood of near-term delivery.

## Slide 4: Ancillary Documents / Staffing Split — Resolved
Odell/Whitfield staffing split question is now finalized: no split required (confirmed "N")
This item is closed and no longer a tracked open point, separate from the ongoing estoppel escalation
Notes: Previously open; now resolved. Softened framing accordingly in underlying tracker and drafting notes. Distinct from the still-open Whitfield/Odell estoppel escalation.

## Slide 5: Closing Timeline Implications
Two outstanding items — Whitfield/Odell estoppel escalation and Seller good standing certificate — are the critical path to closing readiness
If both remain stalled past this week, timeline risk increases materially given board urgency on this call
Recommend board flag continued escalation priority on Whitfield/Odell estoppel and status escalation on good standing certificate
Notes: This is the key ask for the board: visibility into what happens to the closing date if these two items don't move in the next few days. Checklist held open — no terminal marks, no signature page — until both resolve.

## Slide 6: Summary Table
Item | Status | Owner | Change Since Last Update
Estoppels (3 total) | 2 of 3 open — Whitfield/Odell escalated to counsel | Team (escalation follow-up) | Escalated to counsel; no callback yet. Prior reporting discrepancy fully reconciled — 2 open confirmed
Good Standing Certificate (Seller, DE — Whitfield/Sandhurst Real Estate Holdco LLC) | Outstanding — last remaining jurisdiction | Mira (follow-up) | Secretary's Certificate item closed; this is now the sole remaining good-standing item
Ancillary Docs / Staffing Split | Resolved (N — no split) | N/A | Resolved since last update
Notes: One-slide summary for quick board reference; mirrors the current reconciled closing checklist and diligence open items tracker.

## Slide 7: Next Steps
Continue Whitfield/Odell estoppel escalation with counsel and report any status change immediately
Mira to follow up on Whitfield good standing certificate and flag upon receipt
Closing checklist and drafting notes (Sections 4.1, 4.3, 6.2, Article 7) updated to reflect current reconciled status
No substantive agreement terms affected — status references only
Closing checklist and diligence tracker confirmed reconciled and tying out; only two items remain open going into the board call
Notes: Confirm with Dov before the call that these are the only two open items; everything else is tracking to plan. Checklist held open pending resolution of Whitfield estoppel/counsel response and final good standing certificate.