## Signature Pages Tracker
Document | Excluded (Ingrid's Hold) | Signatory Party | Signatory Name/Title | Execution Page Received | Form of Execution | Location/Binder Tab | Status | Notes
Stock Purchase Agreement | No | Seller | TBD - per closing checklist | No | Wet ink | Closing Binder Tab 1 | Outstanding | Awaiting execution copy from seller counsel
Stock Purchase Agreement | No | Buyer | TBD - per closing checklist | No | Wet ink | Closing Binder Tab 1 | Outstanding | Awaiting execution copy from buyer signatory
Asset Purchase Agreement (APA) | Yes | N/A | N/A | N/A | N/A | Excluded | Excluded | Held per Ingrid's instruction - do not include in this closing set
Escrow Agreement | No | Seller | TBD - per closing checklist | No | Wet ink | Closing Binder Tab 2 | Outstanding | Confirm escrow agent counter-signature page
Escrow Agreement | No | Buyer | TBD - per closing checklist | No | Wet ink | Closing Binder Tab 2 | Outstanding | Confirm escrow agent counter-signature page
Escrow Agreement | No | Escrow Agent | TBD - per closing checklist | No | Wet ink | Closing Binder Tab 2 | Outstanding | Coordinate with escrow agent for signature block
Transition Services Agreement | No | Seller | TBD - per closing checklist | No | Wet ink | Closing Binder Tab 3 | Outstanding | Confirm final redline accepted before circulating for signature
Transition Services Agreement | No | Buyer | TBD - per closing checklist | No | Wet ink | Closing Binder Tab 3 | Outstanding | Confirm final redline accepted before circulating for signature
White Oak Lease Consent | No | Landlord (White Oak) | TBD - per closing checklist | No | Wet ink | Closing Binder Tab 4 | Escalated - Pending | Consent escalation in progress per deal status meeting; hold signature page collection until consent confirmed
White Oak Lease Consent | No | Tenant/Seller | TBD - per closing checklist | No | Wet ink | Closing Binder Tab 4 | Outstanding | Dependent on landlord consent resolution
Non-Competition and Non-Solicitation Agreement | No | Key Seller Principals | TBD - per closing checklist | No | Wet ink | Closing Binder Tab 5 | Outstanding | Confirm final list of principals required to sign
Certificate of Good Standing - Delaware | No | N/A (state-issued) | N/A | No | State certificate | Closing Binder Tab 6 | Outstanding | One jurisdiction outstanding per status note; Samir confirming final count
Officer's Certificate - Seller | No | Seller Officer | TBD - per closing checklist | No | Wet ink | Closing Binder Tab 7 | Outstanding | Awaiting finalized disclosure schedules before certificate can be signed
Officer's Certificate - Buyer | No | Buyer Officer | TBD - per closing checklist | No | Wet ink | Closing Binder Tab 7 | Outstanding | Standard closing certificate - no open issues noted
Secretary's Certificate - Seller | No | Seller Secretary | TBD - per closing checklist | No | Wet ink | Closing Binder Tab 7 | Outstanding | Attach organizational documents and resolutions once finalized
Assignment and Assumption Agreement | No | Seller | TBD - per closing checklist | No | Wet ink | Closing Binder Tab 8 | Outstanding | Confirm assigned contracts list matches final disclosure schedule
Assignment and Assumption Agreement | No | Buyer | TBD - per closing checklist | No | Wet ink | Closing Binder Tab 8 | Outstanding | Confirm assigned contracts list matches final disclosure schedule

## Exclusions and Notes
Item | Detail
Exclusion basis | APA excluded from this consolidated signature page set per Ingrid's hold instruction; do not circulate, collect, or bind APA execution pages until hold is lifted
Source | Consolidation reflects Closing Checklist (v3) as revised, plus outcomes of Corporate deal status meeting on Sandhurst platform acquisition
Open dependency - Sandhurst add-on diligence | Coordination ongoing; confirm no further Sandhurst consents outstanding before finalizing signature page set
Open dependency - White Oak lease consent | Escalation in progress; signature pages for related consent document held pending resolution
Open dependency - Good standing certificates | One jurisdiction outstanding; Samir to confirm final count to close out status note
Next step | Recirculate this tracker once White Oak consent and final good standing count are resolved, and once Ingrid lifts the APA hold