## Estoppel Status
Category | Metric | Value | Notes
Landlord Estoppels | Received / Total | 11 of 12 | Unchanged - Whitfield (Sandhurst Real Estate Holdco LLC, Delaware) outstanding
Landlord Estoppels | Outstanding Entity | Sandhurst Real Estate Holdco, LLC | Delaware entity; Whitfield-related
Landlord Estoppels | ETA on Outstanding Cert | None confirmed | No response from registered agent as of this morning; re-checked post-meeting, still no response
Landlord Estoppels | Escalation Status | Deadline letter finalized and issued to Whitfield's counsel | Per Ingrid Solheim (confirmed to Quentin Sarr): letter is finalized and sent, superseding prior registered-agent follow-up path
Landlord Estoppels | Next Action | Monitor for response to deadline letter; follow up before EOD on any movement | Owner: Samir Bhatt
Landlord Estoppels | EOD Follow-Up | Pending - no response as of latest check | Re-confirmed at end of day per checklist owner - still no response received to deadline letter; 11 of 12 fraction carries unchanged into tomorrow
Landlord Estoppels | Registered Agent Follow-Up | Superseded | No longer the active escalation path - deadline letter to counsel now controls
Related Item | MIP Mechanics Receipt | Owned by Quentin | Not a Samir Bhatt item - clarified in chat

## Good Standing Certificates
Category | Metric | Value | Notes
Ardmore Elevator | Request Status | Sent | Samir Bhatt requested good standing certificate for Ardmore Elevator entity
Ardmore Elevator | Response Received | Yes | Ingrid Solheim replied on the Ardmore Elevator Good Standing Request thread
Ardmore Elevator | Owner | Samir Bhatt | Tracking to closing binder inclusion
Ardmore Elevator | Certificate Content | Reviewed - in order | Confirmed against entity chart during status meeting; no discrepancies noted
Ardmore Elevator | Overall Good Standing Count | 12 of 12 confirmed | Per Dov Reinhardt's chat confirmation - full set now complete
Ardmore Elevator | Next Action | Filed in closing binder | Cleared and filed following certificate content review and full-set confirmation

## Change Log
Date/Time | Change | Author
Today, pre-11:00 | Refreshed estoppel fraction ahead of 11:00 status email - no change from prior report, still 11 of 12 back | Samir Bhatt
Today, post-deal status meeting | Confirmed no movement on outstanding Sandhurst/Whitfield estoppel; escalation to Whitfield's counsel remains active; added registered agent follow-up as pending next action | Samir Bhatt
Today, post-meeting | Added Good Standing Certificates section to track Ardmore Elevator request/response with Ingrid Solheim | Samir Bhatt
Today, later | Updated escalation status: deadline letter drafted and sent to Whitfield's counsel per Ingrid Solheim; registered agent follow-up marked superseded; next action shifted to monitoring response to deadline letter | Samir Bhatt
Today, after status meeting | Reviewed Sandhurst checklist status live in meeting - no change to 11 of 12 fraction; added EOD follow-up row for deadline letter response tracking; reviewed and confirmed Ardmore Elevator good standing certificate content as in order, cleared for closing binder filing | Samir Bhatt
Today, afternoon | Updated Good Standing Certificates status to 12 of 12 confirmed per Dov Reinhardt's chat; marked Ardmore Elevator certificate as filed in closing binder | Samir Bhatt
Today, afternoon | Updated Landlord Estoppels escalation status: Ingrid Solheim confirmed to Quentin Sarr that the deadline letter to Whitfield's counsel is finalized and sent | Samir Bhatt
Today, late afternoon | Re-checked deadline letter response status post-meeting - still no response from Whitfield's counsel; EOD follow-up note refreshed to reflect latest check; 11 of 12 estoppel fraction remains unchanged | Samir Bhatt
Today, end of day | Final EOD check per checklist owner protocol: still no response from Whitfield's counsel on deadline letter; 11 of 12 estoppel fraction confirmed unchanged going into tomorrow; Good Standing Certificates remain complete at 12 of 12 with Ardmore Elevator filed | Samir Bhatt