## Article 4-7 Open Items
Item # | APA Section | Topic | Issue | Raised By | Status | Owner | Target Resolution Date
1 | 4.2 | Fundamental Reps | Seller wants knowledge qualifier added to title rep on grain elevator real property | Ingrid Solheim | Open - awaiting seller counsel response - follow up tomorrow | I. Solheim | 2024-06-14
2 | 4.9 | Environmental Reps | Phase I report flags historic fuel storage tank at Ardmore site; need indemnity carve-out or specific rep | Diligence team | Open - drafting specific indemnity language - follow up tomorrow | I. Solheim | 2024-06-12
3 | 5.1 | Covenants - Interim Operations | Buyer wants restriction on entering new grain storage contracts >90 days pending closing | Client (Verity Grain) | Open - sent to seller counsel 6/10 - follow up tomorrow | I. Solheim | 2024-06-13
4 | 5.4 | Employee Matters | Need list of Ardmore union employees and CBA terms; seller has not produced | Diligence team | Open - follow-up request sent - follow up tomorrow | Associate (junior) | 2024-06-11
5 | 6.3 | Closing Conditions | Confirm HSR waiting period expiration date and any second request risk | Ingrid Solheim | Open - monitoring, no second request received - follow up tomorrow | I. Solheim | 2024-06-20
6 | 7.2 | Indemnification Cap/Basket | Seller pushing for lower cap (5% of purchase price); buyer wants 10% | Client (Verity Grain) | Open - business point, escalated to partner; fee estimate through closing confirmed to Imelda today (doc-000207), supplier dispute line reflects settled no-counterclaim decision | Partner | 2024-06-14
7 | 4.11 | Material Contracts | Grain elevator storage agreement with Hollstead Cooperative has change-of-control consent requirement | Diligence team | Open - consent request drafted, not yet sent - follow up tomorrow | I. Solheim | 2024-06-12
8 | 7.5 | Survival Periods | Environmental rep survival - seller wants 12 months, buyer wants through statute of limitations | Ingrid Solheim | Resolved - pincite/citation items closed out today per Article 4-7 Redlines Closeout memo | I. Solheim | 2024-06-13
9 | 6.7 | Title Insurance | Title commitment shows unreleased mechanic's lien from 2019 elevator repair | Diligence team | Open - lien release requested from contractor - follow up tomorrow | Associate (junior) | 2024-06-18
10 | 5.6 | Non-Compete | Confirm scope of seller's post-closing non-compete covers grain storage and merchandising within 100 miles | Ingrid Solheim | Resolved - language finalized 6/9 | I. Solheim | 2024-06-09
11 | N/A - Cross-Reference | MIP Figures Receipt Confirmation | Whitfield/Sandhurst receipt of MIP figures unconfirmed; escalation moved from calls to a formal deadline letter to Whitfield sent today; owned by Quentin/Samir workstream, outside APA diligence scope but tracked here for visibility - no impact on Ardmore closing timeline | Ingrid Solheim (escalation only) | Open - deadline letter sent to Whitfield today; no response yet; loop remains open pending his confirmation or push to Sandhurst - follow up tomorrow | Quentin / Samir | 2024-06-13