## Closing Timeline
Workstream | Task | Owner | Due Date | Status
Corporate | Finalize Asset Purchase Agreement | Reinhardt / Verity Grain GC | 2025-06-02 | In redline
Corporate | Board resolutions - Verity Grain | Verity Grain Corp Sec | 2025-06-03 | Not started
Corporate | Board/member consent - Ardmore Elevator | Ardmore counsel | 2025-06-03 | Not started
Diligence | Final environmental report - grain elevator sites | Environmental counsel | 2025-05-28 | In progress
Diligence | UCC lien search update | Paralegal team | 2025-05-27 | Complete
Diligence | Material contracts consent tracker close-out | Associate team | 2025-05-30 | In progress
Financing | Payoff letters - existing lender | Verity Grain Treasury | 2025-05-29 | Requested
Financing | Financing commitment letter - acquisition facility | Lender counsel | 2025-05-30 | In progress
Regulatory | HSR waiting period expiration | Antitrust counsel | 2025-06-01 | Tracking - early termination requested
Real Estate | Title commitments - elevator facilities (3 sites) | Title company / RE counsel | 2025-05-29 | Two of three received
Real Estate | Survey updates | Surveyor | 2025-05-30 | In progress
Closing Mechanics | Closing checklist circulated to all parties | Reinhardt | 2025-05-26 | Complete
Closing Mechanics | Signature pages collected | Associate team | 2025-06-04 | Not started
Closing Mechanics | Funds flow memo finalized | Reinhardt / Treasury | 2025-06-04 | Draft circulated
Closing | Target closing date | All parties | 2025-06-05 | On track