## Entity Checklist
Entity Name | Jurisdiction | Item | Requested Date | Status | Received Date | Notes
Ardmore Grain Elevator Co. | Kansas | Certificate of Good Standing | 2025-05-12 | Received | 2025-05-19 | Provided by per-lucien-abara
Ardmore Grain Elevator Co. | Kansas | Certified Articles of Incorporation | 2025-05-12 | Received | 2025-05-19 | On file
Ardmore Grain Elevator Co. | Kansas | Bylaws (certified) | 2025-05-12 | Received | 2025-05-20
Ardmore Grain Elevator Co. | Kansas | UCC Lien Search | 2025-05-12 | Received | 2025-05-21 | 3 filings found, see UCC schedule
Ardmore Elevator Holdings LLC | Delaware | Certificate of Good Standing | 2025-05-12 | Received | 2025-05-19 | Provided by per-ingrid-solheim
Ardmore Elevator Holdings LLC | Delaware | Certified LLC Agreement | 2025-05-12 | Received | 2025-05-19
Ardmore Elevator Holdings LLC | Delaware | Certificate of Formation | 2025-05-12 | Received | 2025-05-20
Ardmore Elevator Holdings LLC | Delaware | UCC Lien Search | 2025-05-12 | Received | 2025-05-21 | 1 filing found, see UCC schedule
Ardmore Terminal Services Inc. | Kansas | Certificate of Good Standing | 2025-05-12 | Outstanding |  | Follow-up sent 5/22 to per-lucien-abara
Ardmore Terminal Services Inc. | Kansas | Certified Articles of Incorporation | 2025-05-12 | Received | 2025-05-19
Ardmore Terminal Services Inc. | Kansas | Bylaws (certified) | 2025-05-12 | Received | 2025-05-20
Ardmore Terminal Services Inc. | Kansas | UCC Lien Search | 2025-05-12 | Outstanding |  | Search ordered, pending vendor return
Ardmore Farm Supply LLC | Kansas | Certificate of Good Standing | 2025-05-12 | Outstanding |  | Follow-up sent 5/22
Ardmore Farm Supply LLC | Kansas | Certified Operating Agreement | 2025-05-12 | Received | 2025-05-20

## Summary
Metric | Value
Total items requested | 14
Items received | 11
Items outstanding | 3
Status | 11 of 14 back
Outstanding entities | Ardmore Terminal Services Inc.; Ardmore Farm Supply LLC
Next action | Escalate outstanding good standing and UCC search for Ardmore Terminal Services Inc. and Ardmore Farm Supply LLC; target close 5/27