## Master Docket
Client | Matter | Deadline Description | Governing Rule/Order | Deadline Date | Days Remaining (as of 2026-01-16) | Owner | Status | Escalation Notes
Coastal Meridian | Regulatory inquiry | Response to second document request from regulator | Agency letter dated 2025-12-19 | 2026-01-30 | 14 | M. Alderidge | On track | Confirmed with owner 2026-01-15; drafts in progress
Coastal Meridian | Credit agreement covenant review | Deliver covenant compliance memo to client | Engagement letter timeline | 2026-01-23 | 7 | R. Fenimore | At risk | No draft circulated as of 2026-01-16; reminder sent
Halden Orthopedics | Renwick non-compete | File opposition to motion to dismiss | Court scheduling order | 2026-01-20 | 4 | S. Okonkwo-Reyes | On track | Draft under partner review since 2026-01-14
Halden Orthopedics | Tessaro malpractice defence | Expert disclosure deadline | FRCP 26(a)(2) / case management order | 2026-02-06 | 21 | S. Okonkwo-Reyes | On track | Expert retained; report pending
Verity Grain | Ardmore elevator acquisition | Closing conditions satisfaction deadline | Purchase agreement Section 9.1 | 2026-01-31 | 15 | T. Vasquez | On track | Diligence items 2 of 3 cleared
Verity Grain | Hollstead supply dispute | Answer to counterclaim due | Court order dated 2025-12-30 | 2026-01-19 | 3 | D. Okafor | Escalated | No response drafted as of 2026-01-16; escalated to matter partner 2026-01-15
Pellumbra | Ravenna collaboration agreement | Deliver markup to counterparty | Negotiation timeline (non-court) | 2026-01-22 | 6 | L. Barrantes | On track | Markup 90% complete per 2026-01-15 check-in
Pellumbra | Series C disclosure schedule | Finalize disclosure schedule for signing | Internal closing timeline | 2026-01-27 | 11 | L. Barrantes | On track | Awaiting final IP schedule inputs from client
Pellumbra | Cross-border clinical data assessment | Submit data transfer impact assessment | Internal regulatory deadline | 2026-02-10 | 25 | N. Whitfield | On track | Kickoff call held 2026-01-13
Northmoor | Sandhurst platform acquisition | HSR waiting period expiration | HSR Act, second request timeline | 2026-01-25 | 9 | T. Vasquez | On track | No second request issued to date
Northmoor | Sandhurst add-on diligence | Complete Q&A responses to buyer counsel | Deal timeline (non-court) | 2026-01-21 | 5 | T. Vasquez | At risk | Outstanding items flagged to owner 2026-01-16
Sable Ridge | Driver meal-break collective action | Opposition to conditional certification motion due | Court order dated 2025-12-22 | 2026-01-19 | 3 | D. Okafor | Escalated | Draft incomplete; escalated to matter partner 2026-01-15 and 2026-01-16

## Escalations Log
Date Flagged | Client | Matter | Deadline | Days Remaining | Escalated To | Reminder Count | Response Received
2026-01-15 | Verity Grain | Hollstead supply dispute | 2026-01-19 | 3 | Matter Partner - D. Okafor | 2 | No
2026-01-16 | Sable Ridge | Driver meal-break collective action | 2026-01-19 | 3 | Matter Partner - D. Okafor | 3 | No
2026-01-16 | Northmoor | Sandhurst add-on diligence | 2026-01-21 | 5 | T. Vasquez | 1 | No
2026-01-15 | Coastal Meridian | Credit agreement covenant review | 2026-01-23 | 7 | R. Fenimore | 1 | No