## Active Deadlines
Client | Matter | Deadline Description | Deadline Date | Days Remaining | Owner | Status | Source/Authority
Coastal Meridian | Regulatory inquiry | Response to agency information request | 2025-06-16 | 7 | Bennett-Ashworth | Open - drafting in progress | Agency letter dated 2025-05-19
Coastal Meridian | Credit agreement covenant review | Deliver covenant compliance opinion to lender | 2025-06-20 | 11 | Bennett-Ashworth | Open - awaiting financials from client | Credit Agreement §7.2
Halden Orthopedics | Renwick non-compete | Opposition to motion to dismiss due | 2025-06-13 | 4 | Per-Lucien Abara | Open - draft under review | Court scheduling order
Halden Orthopedics | Tessaro malpractice defence | Expert disclosure deadline | 2025-06-30 | 21 | Per-Lucien Abara | Open - expert retained, report pending | FRCP 26(a)(2) / court order
Verity Grain | Ardmore elevator acquisition | Closing conditions deadline | 2025-06-25 | 16 | Bennett-Ashworth | Open - chain-of-access routing decision pending | Purchase Agreement §9.1
Verity Grain | Hollstead supply dispute | Answer to counterclaim due | 2025-06-17 | 8 | Per-Thandiwe Mokoena (chasing owner) | Open - owner not yet assigned draft | Court docket entry #14
Pellumbra | Ravenna collaboration agreement | Exclusivity period expiration | 2025-06-22 | 13 | Bennett-Ashworth | Open - term sheet negotiation ongoing | Term Sheet §4
Pellumbra | Series C disclosure schedule | Disclosure schedule delivery to investors | 2025-06-14 | 5 | Bennett-Ashworth | Open - awaiting final IP schedule | Stock Purchase Agreement §3
Pellumbra | Cross-border clinical data assessment | Regulatory filing deadline (EU data transfer) | 2025-06-28 | 19 | Per-Lucien Abara | Open - assessment in draft | GDPR Art. 46 transfer mechanism
Northmoor | Sandhurst platform acquisition | Antitrust filing deadline (HSR waiting period) | 2025-06-18 | 9 | Bennett-Ashworth | Open - filing drafted, awaiting sign-off | HSR Act 15 U.S.C. §18a
Northmoor | Sandhurst add-on diligence | Diligence report delivery to client | 2025-06-15 | 6 | Per-Lucien Abara | Open - final review pending | Engagement letter timeline
Sable Ridge | Driver meal-break collective action | Reply brief filing | 2025-06-09 | 0 | Bennett-Ashworth | Filed today per instruction — confirmed | Court order dated 2025-05-27

## Escalations
Client | Matter | Issue | Escalated To | Date Escalated | Resolution Status
Verity Grain | Hollstead supply dispute | No owner confirmed for Answer draft with 8 days remaining | Bennett-Ashworth | 2025-06-09 | Awaiting assignment
Pellumbra | Cross-border clinical data assessment | Unidentified document referenced in per-lucien-abara chat requires confirmation of scope | Per-Lucien Abara | 2025-06-09 | Confirmed per chat log - closing loop

## Upcoming Meetings
Meeting | Related Matter | Purpose | Status
Ardmore Chain-of-Access Routing Decision | Verity Grain - Ardmore elevator acquisition | Determine document/data access routing ahead of closing | Scheduled