## Docket Sweep
Matter | Deadline Item | Source | Deadline Date | Days Remaining | Owner | Status | At Risk | Notes
Ardmore Elevator (Verity Grain Acquisition) | Good standing filing | Clerk queue cutoff | 2025-05-19 | 0 | Samir | Missed 4:00pm cutoff | TRUE | Escalated to Bennett/Samir at 3:30pm ahead of 4pm cutoff; cutoff missed. Followed up with Samir for confirmation; chasing again on tomorrow's docket call.
Ardmore Elevator (Verity Grain Acquisition) | Chain-of-access issue - deadline unconfirmed | Pending attorney input | TBD |  | Rosalie / Gideon | Awaiting deadline confirmation | TRUE | Gideon has not responded to four pings. Asked Rosalie directly for the specific deadline so it can be calendared and chased.
Sable Ridge | Position Statement - self-signature | Bennett's ruling | 2025-05-19 | 0 | Jamal | Reminder sent EOD deadline | TRUE | Per Bennett's ruling, Jamal must self-sign. EOD today, 0 days remaining. Awaiting confirmation once signed.
Sable Ridge | Related-party conflicts memo - scope pending | Lucien flag | TBD |  | Lucien | Pulled from docket pending scope | FALSE | Unidentified docket entry pulled per Lucien's confirmation; can be re-added once memo scope is settled. Not currently at risk.
Internal - Docket Management Scope | Position Memo: Scope of Docket Management Over Ownership-Escalation-Boundary Questions | Internal governance | Pending Bennett confirmation |  | Thandiwe | Pending standing-rule confirmation | FALSE | Boundary position pending Bennett's confirmation as a standing rule. Tied to daily docket sync cadence; not blocking.
Internal - Reporting | Quarterly escalation frequency data pull | Adaora's request | 2025-05-20 | 1 | Thandiwe | In progress | FALSE | Separate, non-blocking workstream from the docket management scope memo. Due EOD tomorrow.