## 3-26 Active Matters
Matter | Item | Deadline | Days Remaining | Owner | Status | Notes
Ardmore Elevator | Good standing filing | Missed 4pm 12/12 | 0 | Lucien | Open | Carried forward from 3/25 EOD sweep. Samir non-responsive by EOD 12/12; ownership reassigned to Lucien per Bennett's confirmation. Sole open Ardmore item. 0 days remaining, deadline already missed — requires immediate action. Confirmation meeting scheduled to verify status with Lucien.
Ardmore Elevator | Chain-of-access routing | 12/12 | 0 | Samir | Closed | Logged closed 12/12 per Bennett's instruction. Distinct docket line from good standing filing. No further action.
Ardmore Elevator | Position Statement correction (Hyun-woo) | N/A | N/A | Hyun-woo | No docket action | Hyun-woo corrected Jamal's characterization of the Position Statement in chat 3/26; Thandiwe confirmed this is not being routed to any docket status change. Logged for record only — no deadline, no owner change, no open exposure created.

## Cross-Check vs 3-25 EOD
Item | 3/25 EOD Status | 3/26 Status | Change | Notes
Ardmore good standing filing | Open — flagged owner-unresponsive for 3/26 docket call | Open — reassigned to Lucien; confirmation meeting scheduled | Owner changed: Samir to Lucien; confirmation meeting added | Escalation from 3/25 sweep confirmed and actioned on 3/25 docket call per Bennett and Rosalie. Remains 0 days remaining; deadline missed 4pm 12/12. Confirmation meeting scheduled 3/26 to verify Lucien's progress.
Ardmore chain-of-access routing | Closed 12/12 (Samir) | Closed 12/12 (Samir) | No change | Carried forward as closed; no open exposure.
Read-aloud To/CC policy | Confirmed firmwide, closed 12/12 | Closed | No change | Logged for the record; no docket action required.
Position Statement characterization | Not previously logged | Corrected by Hyun-woo; no docket action taken | New line item added | Jamal's characterization corrected by Hyun-woo 3/26; Thandiwe confirmed no routing to docket status. No deadline or owner implications.

## Escalation Log
Date | Item | Action | Result
3/25 | Ardmore good standing filing | Flagged owner-unresponsive for 3/26 docket call per prior sweep | Carried into 3/25 docket call same day per revision to doc-379
3/25 | Ardmore good standing filing | Bennett's EOD deadline for Samir to surface or be replaced | Samir did not surface by EOD
3/25 | Ardmore good standing filing | Ownership reassigned | Lucien confirmed as new owner
3/26 | Ardmore good standing filing | Carried forward as sole open Ardmore item under Lucien | Open, 0 days remaining, deadline already missed — active exposure
3/26 | Ardmore good standing filing | Confirmation meeting scheduled with Lucien to verify status | Pending — outcome to be logged on next sweep
3/26 | Position Statement characterization | Hyun-woo corrected Jamal's characterization in chat; Thandiwe confirmed not routing to docket status change | No docket action taken; logged for record only