## Active Matter Deadlines
Matter | Deadline Description | Docketed Date/Time | Days Remaining | Owner | Status
Ardmore Elevator - Good Standing Filing | File certificate of good standing per docket text | Today, 4:00 PM | 0 | Samir | MISSED - unresponsive, escalated to Bennett and clerk-queue check per Adaora's instruction
Ardmore Elevator - Chain-of-Access Routing Decision | Internal routing decision on chain-of-access (not court-imposed) | Today, EOD | 0 | Samir (confirmed per Bennett) | Ownership confirmed today; tracked separate from good-standing filing
Sable Ridge - Driver Meal-Break Collective Action | Opt-in notice period tracking per court order | Per Sable Ridge tracker - see separate document |  | TBD | See dedicated tracker document
[Open Sign-Off Item 1] | Pending sign-off per Ardmore chain-of-access status doc | Unchanged - see Ardmore Chain-of-Access Docket Status doc |  | Unconfirmed | Open - no deadline change from today's chats
[Open Sign-Off Item 2] | Pending sign-off per Ardmore chain-of-access status doc | Unchanged - see Ardmore Chain-of-Access Docket Status doc |  | Unconfirmed | Open - no deadline change from today's chats
[Open Sign-Off Item 3] | Pending sign-off per Ardmore chain-of-access status doc | Unchanged - see Ardmore Chain-of-Access Docket Status doc |  | Unconfirmed | Open - no deadline change from today's chats
Lucien Abara - Separate Tracking Item | Clarification requested on EOD deadline scope (routing decision vs. ownership claim) | Awaiting Lucien's response |  | Lucien | Tracked apart from the three open sign-off items per today's revision

## At-Risk Summary
Matter | Deadline | Days Remaining | Risk Note
Ardmore Elevator - Good Standing Filing | Today, 4:00 PM | 0 | Deadline missed. Samir unresponsive after repeated chases. Escalated to Bennett; Adaora instructed direct clerk-queue check. To be flagged on tomorrow's docket call absent reply.
Ardmore Elevator - Chain-of-Access Routing Decision | Today, EOD | 0 | Ownership now confirmed as Samir per Bennett's clarification. Closed as an open-ownership question; monitor for compliance with EOD commitment.