## Active Matters - Deadlines
Matter | Deadline Description | Source (Docket Text / Statute) | Deadline Date | Days Remaining | Status | Owner | Notes
Pryor v. [Defendant] | Reply brief deadline | Docket text - court order dated per docket | 2025-06-13 | 14 | Calendared | Rosalie | Confirmed to Rosalie 2x; 14 days remaining as of 5/30.
Sable Ridge - Driver Meal-Break Collective Action | Opposition brief - filed | Docket text | 2025-05-23 | 0 | Closed out - filed on time | Rosalie | No further action; matter closed for this filing.
Sable Ridge - Driver Meal-Break Collective Action | Document review tracker - open coding/privilege issues | Internal tracker, not court-imposed |  |  | Follow-up sent to Noor, pressing for EOD status | Noor | No docket deadline attaches to the tracker itself; internal management item only.
Sable Ridge - Driver Meal-Break Collective Action | Privilege log Nos. 5 and 8 - resolution | Internal tracker |  |  | Resolved - marked Final | Noor | Confirmed resolved; no docket deadline attaches.
Sable Ridge - Driver Meal-Break Collective Action | Privilege direction date (flagged in doc-000030 review) | Not yet tied to a calendared date |  |  | Flagged - awaiting confirmed date | TBD | Review note added; no content removed. Needs calendared date before next report.
Sable Ridge - Driver Meal-Break Collective Action | Mediation call scheduling window (flagged in doc-000030 review) | Not yet tied to a calendared date |  |  | Flagged - awaiting confirmed date | TBD | Review note added; scheduling window not yet confirmed with a specific date.
Sable Ridge - Driver Meal-Break Collective Action | RIF review timeline (flagged in doc-000030 review) | Not yet tied to a calendared date |  |  | Flagged - awaiting confirmed status | TBD | Review note added; status not yet confirmed.
Internal Ops - Calendar/IT Sync Issue | Confirmation of fix by IT (calendar/IT sync) | Internal escalation, not court-imposed | 2025-05-30 | 0 | Escalated - 8pm commitment received from Lucien, calendared | Lucien | Fourth follow-up sent. Deadline EOD 5/30 before 8pm, 0 days remaining. Manual workaround in place if unconfirmed by close.

## Summary - Days Remaining Snapsh
Matter | Deadline | Deadline Date | Days Remaining | Escalation Level
Pryor v. [Defendant] | Reply brief deadline | 2025-06-13 | 14 | None - on track
Internal Ops - Calendar/IT Sync Issue | IT confirmation of fix | 2025-05-30 | 0 | Fourth follow-up sent; escalation active
Sable Ridge - Driver Meal-Break Collective Action | Document review tracker status |  |  | Second follow-up sent to Noor