## Open Items
Ref # | Item | Category | Status | Owner | Last Action | Date of Last Action | Escalation Level | Next Step | Closing Impact | Notes
1 | Good Standing Certificate | Corporate | Closed | Ingrid Solheim | Certificate received and confirmed | 2025-06-XX | None | None — closed | None | Closed per revised Corporate/Good Standing tracking; removed from active diligence workstream scope
11 | MIP Figures Receipt Confirmation | Financial / APA | Open | Ingrid Solheim | Deadline letter sent to Whitfield; status reconfirmed at 09:15 meeting — no response received | Today | Third-day escalation — deadline letter issued | Awaiting Whitfield response to deadline letter; fee estimate to be recirculated once figures land | None to date | Escalation moved from informal chase to formal deadline letter; no response received yet; fee estimate updated to reflect increased contingency; confirmed at status meeting that fee estimate remains provisional pending MIP figures
12 | Supplier Counterclaim — File Holder Identification | Litigation / Disputes | Open | Quentin | Escalated past Dov to Dov's supervisor/counsel after three unanswered chases; status confirmed unchanged at 09:15 meeting | Today | Third-day escalation — escalated past primary contact | Awaiting response from Dov's supervisor/counsel; Ingrid to escalate in parallel if no response by tomorrow | None to date | Holder of estoppel certificate file and supplier counterclaim file still unknown; hold-don't-counterclaim recommendation confirmed and unchanged; team agreed at meeting to revisit escalation timeline tomorrow if silence continues
13 | Supplier Dispute — Holding Position | Litigation / Disputes | Closed — position confirmed | Ingrid Solheim | Memorandum issued confirming hold-not-counterclaim position | Today | None | None — position memo on file | Confirmed no closing timeline impact | See Memorandum – Supplier Dispute: Holding Position (No Counterclaim) and Escalation Record
14 | Fee Estimate — Contingency Confirmation | Financial / APA | Open | Ingrid Solheim | Raised at 09:15 status meeting as follow-up to MIP figures delay | Today | None yet — newly opened | Confirm final contingency treatment once MIP figures received from Whitfield | Potential minor impact if fee estimate requires client sign-off before closing | Opened to track fee estimate finalization separately from underlying MIP figures item; owner to circulate updated estimate once Ref #11 resolves