## Correction Note
Date | Item | Prior Type | Corrected Type | Reason | Owner | Status
2025-04-02 | Docket log entries (formerly doc-000030) | .pptx | .xlsx | Docket log entries are tracked/filtered content (dates, owners, days-remaining columns), not a presented deck. Reclassified to match work-product rules. | T. Mokoena | Corrected

## Docket Log
Date | Matter | Item | Deadline | Days Remaining | Owner | Status | Notes
2025-03-31 | Ardmore | Good Standing Filing | 2025-03-31 4:00 PM | 0 | Lucien Abara | Missed - in tomorrow's clerk queue | Days elapsed carries forward, does not reset
2025-03-31 | Ardmore/Whitfield | Non-privilege confirmation (Jamal) | 2025-03-31 EOD | 0 | Jamal | Open - no response | Separate flag raised by Lucien; distinct from good standing item
2025-03-31 | Ardmore/Deshmukh-adjacent | Scope status | Pending |  | Unassigned | Out of scope pending Jamal confirmation | Logged separately from good standing filing
2025-04-01 | Ardmore/Whitfield | Non-privilege confirmation (Jamal) - renewed reminder | 2025-04-01 EOD | 0 | Jamal | Open - reminder sent | Restated deadline, 0 days remaining
2025-04-02 | Ardmore/Deshmukh-adjacent | Scope status | Pending |  | Unassigned | Confirmed out of scope pending Jamal confirmation | Logged separately from Ardmore good standing item, now with Lucien
2025-04-02 | Ardmore/Whitfield | Non-privilege sign-off | 2025-04-03 EOD | 1 | Bennett | Reassigned - new deadline confirmed | Bennett acknowledged ownership; supersedes Jamal chase