# End-of-Day Docket Sweep — 4/1

Prepared by Thandiwe Mokoena, Docket & Calendar Manager. This sweep reflects docket status as of close of business 4/1, incorporating today's chat resolutions on ownership and scope.

## 1. Ardmore Good Standing Filing

Status: OPEN. Original deadline was 4:00pm on 3/31; deadline was missed. Days elapsed carries forward rather than resetting — 1 day elapsed as of 4/1. Filing is now in tomorrow's clerk queue.

Ownership: Now tracked against Lucien Abara, confirmed today following the missed 4:00pm cutoff. Ownership clarification received and acknowledged; days-elapsed count carries forward under new ownership.

Deadline missed: 4:00pm, 3/31

Days elapsed: 1

Owner: Lucien Abara (confirmed 4/1)

Remediation date: requested from Lucien, not yet received

Next action: filing queued with clerk tomorrow; awaiting written remediation date

## 2. Position Statement Sign-Off

Status: UNRESOLVED. Ownership of the sign-off has still not been confirmed by Jamal. Deadline remains end of day (EOD) today, 4/1.

Deadline: EOD, 4/1

Days remaining: 0

Owner: unconfirmed — Jamal has not responded despite repeated chases

Escalation: raised to docket channel following unanswered chases; renewed escalation logged 3/31 and remains active

Next action: escalate again if no confirmation by close of business today

## 3. Ardmore/Whitfield Non-Privilege Confirmation (Separate Flag)

Status: OPEN, tracked as its own line item, separate from the Good Standing Filing split. Raised by Lucien Abara; scope confirmed as Jamal's non-privilege confirmation on Ardmore/Whitfield.

Deadline: EOD, 4/1 (tonight)

Days remaining: 0

Owner: Jamal (confirmation pending)

Chased directly today restating tonight's EOD deadline

Next action: escalate if no confirmation received by end of day

## Escalation Log

| Date | Item | Action | Recipient(s) |
| --- | --- | --- | --- |
| 3/30 | Position Statement sign-off ownership | Chased Jamal; restated EOD 3/31 deadline, 1 day remaining | Jamal |
| 3/30 | Position Statement sign-off ownership | Escalated to docket channel after repeated unanswered chases | Docket channel |
| 3/30 | Ardmore Good Standing Filing | Escalated missed 4:00pm deadline; demanded written confirmation | Hyun-woo, Rosalie |
| 3/31 | Position Statement sign-off ownership | Renewed escalation to docket channel; Jamal still unresponsive | Docket channel |
| 3/31 | Ardmore Good Standing Filing | Confirmed deadline missed, 0 days remaining, moved to clerk queue; tracked against Lucien | Lucien |
| 4/1 | Ardmore Good Standing Filing | Confirmed Lucien as owner; restated deadline and days elapsed; requested remediation date | Lucien |
| 4/1 | Ardmore/Whitfield non-privilege confirmation | Confirmed scope of separate flag; logged as own line; tonight's EOD deadline | Lucien |
| 4/1 | Ardmore/Whitfield non-privilege confirmation | Chased Jamal directly; restated tonight-EOD deadline, 0 days remaining | Jamal |

## Cross-Check Notes

Ardmore Good Standing Filing and the Ardmore/Whitfield non-privilege confirmation are tracked as two separate items per Lucien's 3/31 and 4/1 chat clarifications — not to be merged.

Position Statement sign-off ownership remains open pending Jamal's response; this is the third consecutive day this item has appeared unresolved on the sweep.

Days-elapsed counts on the Good Standing Filing carry forward under Lucien's ownership rather than resetting to zero.

All deadlines calendared per docket text and confirmed chat resolutions, not attorney assurance alone.