## Estoppel & Closing Items
Item # | Workstream | Item | Responsible | Status | Notes | Target Date
1 | Coastal Meridian - Covenant Review | Confirm good standing certificates (all jurisdictions) | Samir Bhatt | Complete | Checklist unchanged per Samir; no open items | 2024-05-10
2 | Coastal Meridian - Covenant Review | Reconcile estoppel certificates against credit agreement covenant schedule | Ulrich Bergmann / Elena Vasquez-Reyes | In Progress | Ulrich confirmed Kowalski-side estoppel resolved per Cecile's relay; one estoppel still outstanding as of latest check-in | 2024-05-17
3 | Coastal Meridian - Covenant Review | Confirm no default/covenant breach representations in estoppel language | Elena Vasquez-Reyes | In Progress | Pending receipt of final outstanding estoppel (Item 2); will reconcile against covenant schedule once received | 2024-05-17
4 | Coastal Meridian - Regulatory Inquiry | Track dependency: regulatory inquiry response timing vs. estoppel reconciliation | Elena Vasquez-Reyes | Monitoring | Cecile flagged both Coastal Meridian and Ravenna as dependencies if reconciliation stays delayed; reassessing now that Kowalski item is resolved | 2024-05-17
5 | Pellumbra - Ravenna Collaboration Agreement | Reconcile Ravenna estoppel/consent items against collaboration agreement schedule | Ulrich Bergmann | In Progress | Per Ulrich's reminder, Coastal Meridian and Ravenna remain paired items; Mira holding off per Ingrid pending resolution | 2024-05-17
6 | Pellumbra - Ravenna Collaboration Agreement | Confirm figures reconcile to Samir's numbers | Mira Chandrasekhar | Complete | Mira confirmed her numbers match Samir's as of prior status meeting; holding further action per Ingrid pending Item 5 | 2024-05-10
7 | Coastal Meridian / Ravenna | Escalate outstanding counterparty calls if unresolved by next status meeting | Ingrid Solheim / Ulrich Bergmann | In Progress | Ulrich's reminder and Cecile's Kowalski confirmation suggest partial progress; escalation still pending for remaining outstanding calls | 2024-05-20
8 | Coastal Meridian / Ravenna | Determine downstream impact on closing timeline if both remain delayed | Elena Vasquez-Reyes | Not Started | Per Cecile: both workstreams flagged as at-risk if reconciliation stays delayed past this week; reassess after Item 2 fully resolved | 2024-05-20
9 | Pellumbra - Ravenna Collaboration Agreement | Confirm latest saved APA version reflects current negotiation status | Quentin Sarr | In Progress | Quentin pulling up latest saved APA for Ingrid's review; to confirm no intervening redlines outstanding | 2024-05-20