## Sweep Summary
Matter | Deadline Type | Court/Source Docket Text | Deadline Date | Days Remaining | Owner | Status | Risk Flag
Verity Grain / Ardmore Elevator Acquisition | Good Standing Filing (Missed Cutoff) | Clerk queue cutoff, per filing office docket text | 2025-06-09 | 0 | Samir | Missed 4:00pm cutoff; refiling required | AT RISK - ESCALATED
Sable Ridge | Position Statement Self-Signature (per Bennett ruling) | Internal deadline per Bennett's ruling, EOD | 2025-06-09 | 0 | Jamal | Reminder sent; confirmation pending | AT RISK
Sable Ridge | Related-Party Conflicts Memo - Docket Entry Scope | Unidentified entry flagged by Lucien, pending scope confirmation | TBD |  | Lucien / Unassigned | Pulled from active docket pending memo scope | HOLD - NOT AT RISK
Firmwide - Ownership Escalation Policy | Quarterly Escalation Frequency Data Pull | Per Adaora's request, firm deadline set by Adaora | 2025-06-10 | 1 | Thandiwe | In progress, non-blocking workstream | ON TRACK

## Escalations This Week
Matter | Escalated To | Reason | Deadline at Time of Escalation | Outcome
Verity Grain / Ardmore Elevator Acquisition | Bennett, Samir | 3:30pm status ahead of 4pm cutoff; ownership correction (Samir, not Bennett) | 2025-06-09 4:00pm | Cutoff missed; logged in status doc
Sable Ridge | Jamal | Self-signature required per Bennett's standing ruling | 2025-06-09 EOD | Pending confirmation

## Resolved This Week
Matter | Deadline Type | Resolution
Today's General Sweep | Various | All entries other than Ardmore resolved same day