## Coding Progress
Batch ID | Reviewer | Docs Assigned | Docs Coded | % Complete | Status | Last Updated
BATCH-001 | Contract Reviewer Team A | 1500 | 1120 |  | In Progress | 2024-06-10
BATCH-002 | Contract Reviewer Team B | 1500 | 1500 |  | Complete - Pending QC | 2024-06-10
BATCH-003 | Contract Reviewer Team A | 1200 | 640 |  | In Progress | 2024-06-10
BATCH-004 | Litigation Group - Overnight | 900 | 900 |  | Complete - Pending QC | 2024-06-10
BATCH-005 | Contract Reviewer Team B | 1000 | 0 |  | Not Started | 2024-06-10
TOTAL

## Open Tagging Queries
Query ID | Batch ID | Doc Range | Issue | Raised By | Status | Notes
TQ-1 | BATCH-001 | Docs 340-355 | Ambiguous responsiveness call on internal marketing emails referencing product specs | Reviewer Team A | Open - Reviewer Note Added | Flagged for Noor's review before overnight batch closes out. REVIEWER NOTE (M. Chandrasekhar): Evidentiary support for a responsiveness call here is thin without the spot-check - do not treat as resolved until Noor confirms; escalate to case team if marketing emails reference product specs tied to asserted claims. FURTHER REVIEW NOTE (M. Chandrasekhar): Status remains open on the current record - no spot-check confirmation from Noor has been logged yet. Do not sign off on this responsiveness call until that confirmation is added. CLOSING REVIEW NOTE (M. Chandrasekhar): Confirmed at today's deal status meeting that Noor's spot-check confirmation is still outstanding; this remains open pending that input and should not be signed off in the interim.
TQ-2 | BATCH-003 | Docs 88-102 | Recurring attachment family coded inconsistently across custodians | Reviewer Team A | Open - Reviewer Note Added | Requesting reviewer align on family-level coding rule. REVIEWER NOTE (M. Chandrasekhar): Inconsistent family-level coding across custodians is enough on its own to call the current tagging unreliable for this range - do not sign off until Reviewer Team A confirms a single coding rule was applied across all custodians; re-code any documents coded under the earlier inconsistent approach. This note is well-supported on the record as described and stands without revision.
TQ-3 | BATCH-004 | Docs 512-520 | Unclear whether draft term sheet falls within date range of request | Litigation Group | Open - Reviewer Note Added | Awaiting confirmation from case team on scope. REVIEWER NOTE (M. Chandrasekhar): Evidentiary support for treating this draft term sheet as within the date range of the request is thin absent the case team's confirmation on scope - do not sign off on inclusion or exclusion until that confirmation is received; if case team confirms the document falls outside the requested date range, code as non-responsive on that basis pending further review. This note is well-supported on the record as described and stands without revision.

## Privilege Calls for Spot-Check
Doc ID Range | Batch ID | Privilege Basis Asserted | Reviewer | Spot-Check Status | Notes
Docs 210-225 | BATCH-002 | Attorney-Client - in-house counsel copied | Reviewer Team B | Requested - not yet reviewed | This may be nothing, but several emails only cc counsel without substantive legal content - worth a second look. REVIEWER NOTE (M. Chandrasekhar): Evidentiary support for the attorney-client basis on this range is thin on the current record - copying counsel without substantive legal content does not, by itself, establish privilege. Do not sign off until the spot-check is completed; if no substantive legal advice is found in the cc'd emails, treat as not privileged on that basis pending further review.
Docs 601-615 | BATCH-004 | Work Product - prepared in anticipation of litigation | Litigation Group | Open - Reviewer Note Added | Date range predates filing; asked overnight team to confirm anticipation-of-litigation timing. REVIEWER NOTE (M. Chandrasekhar): Work-product protection here depends on the anticipation-of-litigation timing being established, and that confirmation from the overnight team is still outstanding - the current basis asserted is thin on this record. Do not sign off the privilege call until timing is confirmed; if the documents predate any reasonable anticipation of litigation, treat as not protected on work-product grounds pending further review. This note is well-supported on the record as described and stands without revision.
Docs 300-310 | BATCH-001 | Attorney-Client | Reviewer Team A | Requested - not yet reviewed | Chain includes non-attorney third party as recipient - flagging for privilege waiver check. See related reviewer note in Document Status Log (Docs 300-310, BATCH-001) for waiver analysis; that note governs sign-off on this entry.

## Document Status Log
Document ID | Description | Status | Notes | Updated By | Date
doc-000011 | Deposition Summary Draft - reviewer markup pass | Reviewed - Signed Off | Reviewer markup added flagging thin evidentiary support in several sections; overstated conclusions tightened; provisions with adequate support signed off. Original drafting retained; no underlying substance rewritten. REVIEWER NOTE (M. Chandrasekhar): Reviewed Noor's markup pass against the underlying record - the tightening of overstated conclusions and the sign-off on adequately supported provisions are both well-supported as described. No further thin-evidence issues identified on this pass; sign-off stands. | Noor Haddad | 2024-06-10
doc-000003 | Research Memo: Enforceability of Choice-of-Law Provision Under Delaware's Most-Significant-Relationship Test | Provisional - Pending Research (Reviewer Note Added) | Closing status note added under Open Items; Ohio caselaw search and related analysis remain incomplete; conclusions framed as provisional pending that follow-up. REVIEWER NOTE (M. Chandrasekhar): Evidentiary support for the current conclusion is thin absent the Ohio caselaw comparison - the memo's provisional framing is appropriate and should stand as-is; do not read the current conclusion as settled. Sections addressing Delaware's most-significant-relationship factors that are supported by the caselaw already cited are sound and signed off; do not revise those pending the Ohio follow-up. Original drafting retained. | Noor Haddad | 2024-06-10
Privilege Log Nos. 5, 8 | Privilege log entries flagged for spot-check | Resolved | Confirmed resolved following follow-up with Hyun-woo on the open question previously raised; no further action needed on these entries. | Noor Haddad | 2024-06-10
Docs 300-310 (BATCH-001) | Privilege spot-check - attorney-client basis, non-attorney third-party recipient on chain | Open - Reviewer Note Added | REVIEWER NOTE (M. Chandrasekhar): The waiver question here turns on the third party's role and whether disclosure was inadvertent or under a common-interest arrangement - neither is established on the current record. Do not sign off the privilege call until Reviewer Team A confirms the third party's status; if no common-interest or agency basis is confirmed, treat as waived as to that chain pending further review. This note remains well-supported on the current record and stands without revision pending Reviewer Team A's confirmation. | Mira Chandrasekhar | 2024-06-10
Sable Ridge Triage - EOD Update | End-of-day triage resolutions on Sable Ridge witness/exhibit tracker and deposition summary workstream | Partially Resolved - One Open Loop | Closed today: (1) Ex. 17 custodian note on witness/exhibit list - resolved; (2) Ulrich/Sandhurst holdout - resolved as not applicable, confirmed Gideon's matter per Bennett; (3) doc-000089 source/owner triage item - closed per Klara's clarification. Remaining open loop for tomorrow: driver meal-break deposition transcript still pending from Petra; deposition summary framework cannot progress to witness-testimony sections until transcript is received. REVIEWER NOTE (M. Chandrasekhar): The three closed items above are adequately supported on the record as described (custodian note, holdout confirmation, and source/owner clarification each trace to a named confirming source) and are signed off as resolved. Note the Sandhurst reference here is unrelated to the separate corporate-side Sandhurst checklist item on today's deal status meeting agenda; no cross-reference or additional confirmation is needed for that distinct workstream. The remaining open loop on the meal-break transcript is correctly carried forward as open - do not treat the deposition summary framework as complete for witness-testimony sections until the transcript is received and incorporated. | Noor Haddad | 2024-06-10