## Overage Summary
Line Item | Category | Driver | Foreseeable at Budget-Setting? | Status | Notes
Approved Budget (Baseline) | Budget | N/A | N/A | Confirmed | Baseline figure per original engagement budget approval; not restated pending Desmond detail
Enforcement-Inquiry Expansion | Overage Driver 1 | Enforcement inquiry scope growth | Not foreseeable | Identified — amount pending | Scope expansion beyond original inquiry footprint; drives incremental hours not contemplated at budget-setting
Second Request Discovery Volume | Overage Driver 2 | Second Request document volume | Partially foreseeable | Identified — amount pending | Volume materially exceeded initial estimate following certified service date and confirmed clock; distinguish foreseeable baseline discovery cost from volume-driven excess
Itemized Line-Item Detail (Desmond) | Pending Input | N/A | N/A | Outstanding — requested from Desmond | Marked-up line-item billing detail requested; committed end-of-week delivery of corrected invoice regardless of receipt
Revised Run-Rate | Pending Calculation | N/A | N/A | Not yet calculable | Withheld pending itemized detail; no figures to be quoted until Desmond's input is incorporated or the end-of-week deadline passes

## Driver Detail - Enforcement Inq
Sub-Item | Description | Hours/Fees (Pending) | Foreseeable? | Support
Scope expansion tasks | Additional inquiry response work beyond original engagement letter scope | TBD - pending Desmond | No | See record; to be reconciled against original scope letter
Related staffing time | Associate and paralegal time attributable to expanded inquiry | TBD - pending Desmond | No | Pending itemized time entries

## Driver Detail - Second Request
Sub-Item | Description | Hours/Fees (Pending) | Foreseeable? | Support
Document volume above estimate | Volume received exceeded initial per-request estimate | TBD - pending Desmond | Partially | Clock runs from certified service date; Adaora's written date confirmation on file
Review team scaling | Incremental review resources added to meet Second Request timeline | TBD - pending Desmond | Partially | Pending itemized time entries