## Summary
Item | Amount (USD)
Original Budget | 185000
Actual Fees to Date | 238450
Total Overage | 53450
Overage as % of Budget | 28.9%
Prepared By | Bennett (owner) / data pulled by Thandiwe
Status | FINAL — reviewed by Managing Partner ahead of Thursday board meeting. Thursday board exposure estimate confirmed with Marguerite Oyelara. Second Request scope confirmed and formal HSR deadline/scope response sent to Marguerite Oyelara; no open items remain in the Discovery lines below. Non-party discovery status is being tracked separately by Thandiwe and is not a factor in the figures or scope confirmation reflected here.

## Itemized Breakdown
Category | Budgeted (USD) | Actual (USD) | Overage (USD) | Driver / Explanation
Discovery — Document Review | 65000 | 92300 | 27300 | Second Request production scope confirmed as expanded beyond original estimate; volume increase reflected in restated figures. Scope confirmation closes this line — no further revision expected. HSR deadline/scope response formally communicated to opposing counsel (Marguerite Oyelara); no impact on figures above.
Discovery — Second Request Response Drafting | 20000 | 31200 | 11200 | Scope confirmation received; additional revision rounds attributable to confirmed expanded scope, not open-ended. Line considered closed.
Legal Research & Memoranda | 15000 | 17800 | 2800 | Additional research required on estoppel count overlap
Depositions & Witness Prep | 30000 | 33150 | 3150 | One additional witness prep session added
Court Filings & Motion Practice | 25000 | 28000 | 3000 | Unplanned motion in response to opposing filing
Case Strategy / Partner Time | 20000 | 24500 | 4500 | Additional partner-level strategy sessions
Administrative / Support | 10000 | 11500 | 1500 | Proportional increase tied to overall matter volume
Total | 185000 | 238450 | 53450

## Ownership & Accountability Note
Note
Bennett is the accountable owner of this write-up per Managing Partner direction.
Thandiwe assisted in pulling and quantifying the underlying figures only; not accountable for the write-up itself.
Due before Thursday's board meeting — this version is final for that purpose.
Thursday board exposure estimate has been confirmed with Marguerite Oyelara; no further confirmation is outstanding ahead of the board meeting.
This overage does not include any write-off; no amount here has been forgiven or reduced against the client.
If any portion of this overage is proposed for write-off, amounts over $25,000 require Managing Partner sign-off in writing, with the reason stated in the same message.
Second Request scope confirmation has been received; Discovery line items above reflect the confirmed scope and are final for purposes of this review — no further scope changes are anticipated. The definitive HSR deadline/scope response has since been sent to Marguerite Oyelara, formally closing this item on the client-facing side.
No write-off has been proposed or approved as of this version; figures reflect actual fees incurred only.
This report addresses fee overage on this matter only. It has no bearing on, and does not address, any separate deal-closing timeline decision (e.g., quarter-close scheduling) on unrelated matters.
For the avoidance of doubt: this report also has no bearing on, and does not address, MIP mechanics or any related compensation question raised separately by Saoirse Mulvaney. That matter is being answered directly and on its own timeline, outside this document.
Non-party discovery inquiries (raised separately by Thandiwe) are being handled on their own track and do not affect the Second Request scope, HSR deadline confirmation, or figures reported above.