## Spent-to-Date
Timekeeper/Category | Role | Hours to Date | Rate | Fees to Date
Dov Reinhardt | Partner | 62.5 | 950
Samir | Senior Associate | 118 | 650
Ingrid | Senior Associate | 96.5 | 650
Odell | Associate | 74 | 495
Whitfield | Associate | 69.5 | 495
Paralegal / Closing Support | Paralegal | 41 | 285
Total Fees to Date

## Through-Closing Projection
Scenario | Milestone | Target Date | Additional Hours (Est.) | Blended Rate | Additional Fees | Total Spent-to-Date + Projection
A - Counterclaim Resolved Pre-Closing | Good standing cert. received | 2025-04-11 | 4 | 650
A - Counterclaim Resolved Pre-Closing | Both estoppels received | 2025-04-14 | 18 | 650
A - Counterclaim Resolved Pre-Closing | Ancillary docs/checklist split cleared (Odell/Whitfield) | 2025-04-15 | 10 | 550
A - Counterclaim Resolved Pre-Closing | Closing | 2025-04-18 | 26 | 700
A - Total Through Closing |  | 2025-04-18
B - Counterclaim Unresolved, Escrow Holdback at Closing | Good standing cert. received | 2025-04-11 | 4 | 650
B - Counterclaim Unresolved, Escrow Holdback at Closing | Both estoppels received | 2025-04-14 | 18 | 650
B - Counterclaim Unresolved, Escrow Holdback at Closing | Ancillary docs/checklist split cleared (Odell/Whitfield) | 2025-04-15 | 10 | 550
B - Counterclaim Unresolved, Escrow Holdback at Closing | Escrow holdback mechanics drafted/negotiated | 2025-04-16 | 22 | 750
B - Counterclaim Unresolved, Escrow Holdback at Closing | Closing | 2025-04-18 | 30 | 700
B - Total Through Closing |  | 2025-04-18

## Closing Conditions at Risk
Condition Precedent | Status | Owner | Risk to Timeline
Good standing certificates | 1 entity outstanding | Samir/Ingrid | Low — expected 2025-04-11
Lease estoppels | 2 outstanding (of total set) | Samir/Ingrid, tracking Gideon's rates table | Medium — expected 2025-04-14
Ancillary docs vs. checklist ownership split | Resolved — Odell/Whitfield confirmed split, checklist updated | Odell/Whitfield | Low — no longer a blocker; monitor for follow-through