## Open Items
Item # | Workstream | Description | Document/Request Ref | Responsible Party | Status | Priority | Date Opened | Target Close Date | Notes
1 | Real Estate | Estoppel certificate outstanding from Whitfield (landlord) for Sandhurst HQ lease | Lease Schedule 3.1(a) | Landlord Counsel (Whitfield) | Escalated - Client Involved | High | 2024-05-20 | 2024-06-14 | Second follow-up sent 6/3; escalation call held 6/5. Landlord counsel remained non-responsive for 9 business days; matter escalated further to client (Samir Bhatt) and deal team on 6/6 per team correspondence. Quentin Sarr flagged status via chat; Dov Reinhardt looped in on next steps. Client now engaging landlord directly to press for signature. Status confirmed on today's deal status call: client reports landlord has verbally agreed to sign but is requesting minor non-substantive edits to the estoppel form; deal team to review redline once received. Revised target close date reflects escalation timeline; team to reassess if signature not received by 6/12. Ownership update: Quentin now owns closeout of the Whitfield/Odell estoppel certificate; Mira has stood down from directly chasing this item. Per team consensus, this remains the sole outstanding item blocking issuance of the signature page; still pending landlord counsel callback.
2 | Real Estate | Estoppel certificate - Sandhurst distribution facility (Ohio) | Lease Schedule 3.1(b) | Landlord Counsel (Ohio LL) | Received | Medium | 2024-05-20 | 2024-05-30 | Executed and on file.
3 | Corporate | Sandhurst cap table reconciliation vs. Schedule 4.2 | Disclosure Schedule 4.2 | Target Counsel | Open | High | 2024-05-15 | 2024-06-08 | Discrepancy of 1,200 options unaccounted for; awaiting revised cap table. Discussed on deal status call - target counsel indicated the discrepancy relates to a batch of early-exercise options not yet reflected in the option ledger; revised cap table expected by 6/10. Deal team to confirm reconciliation ties out before signing.
4 | Material Contracts | Change of control consent - largest customer (Meridian Foods MSA) | Contract Schedule 4.10(c) | Target Management | In Progress | High | 2024-05-22 | 2024-06-12 | Draft consent letter circulated; customer legal reviewing.
5 | Material Contracts | Change of control consent - equipment financing facility | Contract Schedule 4.10(f) | Lender Counsel | Open | Medium | 2024-05-22 | 2024-06-14 | Lender requested updated financials before consent.
6 | IP | Confirm assignment of key patent from founder to Sandhurst entity | IP Schedule 4.12 | Target IP Counsel | Received | High | 2024-05-10 | 2024-05-25 | Assignment recorded with USPTO; confirmation received.
7 | Employment | Change-in-control payment calculations for 3 executives | Employment Schedule 4.14 | Target HR / Comp Consultant | In Progress | Medium | 2024-05-25 | 2024-06-15 | Awaiting final comp consultant sign-off on 280G analysis.
8 | Litigation | Pending wage-and-hour claim disclosure (Sandhurst warehouse) | Litigation Schedule 4.15 | Target Counsel | Open | High | 2024-05-28 | 2024-06-10 | Requested complaint and any settlement demand; not yet produced. Raised again on deal status call - target counsel committed to producing the complaint and demand letter by end of week; team flagged this as a priority given the 6/10 target close date.
9 | Environmental | Phase I ESA - Ohio distribution facility | Env. Schedule 4.16 | Environmental Consultant | In Progress | Medium | 2024-05-18 | 2024-06-20 | Site visit completed 6/1; report expected week of 6/17.
10 | Tax | Confirm no outstanding state sales tax audits | Tax Schedule 4.17 | Target Tax Advisor | Received | Low | 2024-05-12 | 2024-05-30 | Confirmed clean via state tax clearance letters.
11 | Insurance | Certificate of insurance and D&O tail coverage quote | Insurance Schedule 4.18 | Target Broker | Open | Medium | 2024-05-29 | 2024-06-13 | Tail quote requested; broker says 5-7 business day turnaround.
12 | Corporate | Board resolutions authorizing sale - confirm quorum and no dissenting votes | Corporate Schedule 4.1 | Target Corporate Secretary | Received | Low | 2024-05-14 | 2024-05-22 | Executed unanimous written consent on file.