## Closing Checklist
Item # | Deliverable | Party Responsible | Status | Date Completed / Due | Notes
1 | Delaware good standing certificate - Sandhurst Holdings, Inc. | Quentin Sarr | Complete | 12/12 | Certificate received and reviewed; no deficiencies noted
2 | Delaware good standing certificate - Sandhurst Operating, LLC | Quentin Sarr | Complete | 12/12 | Certificate received and reviewed; no deficiencies noted
2a | Ohio (OH) good standing certificate - Sandhurst Operating, LLC | Quentin Sarr | 11 of 12 | TBD | Status corrected per Samir's confirmation (chat) reflecting current plan block; certificate collection remains in progress
3 | Estoppel certificate - Odell Properties (landlord, HQ lease) | Quentin Sarr | Outstanding | TBD | Requested 12/05; no response yet. Follow-up call placed 12/12
4 | Estoppel certificate - Whitfield Logistics Center (landlord, warehouse lease) | Quentin Sarr | Outstanding | TBD | Requested 12/05; landlord counsel confirmed receipt 12/10, drafting response. Escalation path: if not received by 12/16, deal team to have client contact land owner directly per today's status meeting. REVIEW NOTE (post-EOD): Today's end-of-day status update and deal team discussion described this item as resolved; however, this checklist's status field still reads 'Outstanding' and no estoppel document has been logged as received. Item should not be marked Complete until the actual certificate is received and documented in the file - verbal or chat confirmation is not sufficient evidentiary basis to close this item.
5 | UCC lien search - Delaware Secretary of State | Quentin Sarr | Complete | 12/08 | No liens outside permitted encumbrances schedule
6 | UCC lien search - Sandhurst principal place of business (state) | Quentin Sarr | Complete | 12/08 | No liens outside permitted encumbrances schedule
7 | Litigation search - state and federal dockets | Associate (litigation team) | Complete | 12/09 | No pending or threatened litigation identified
8 | Material contracts consent requirements review | Deal team | In progress | 12/14 | Two contracts require third-party consent to assignment; notices being prepared
9 | Officer's certificate - Sandhurst Holdings | Client counsel | Not started | TBD | To be circulated after estoppels resolved
10 | Closing set assembly and signature pages | Quentin Sarr | Not started | TBD | Pending completion of items 3, 4, 9. REVIEW NOTE: Confirmed with Ingrid that the matter-association tagging for this item resolves to 'Sandhurst Platform Acquisition,' consistent with all other rows on this checklist; this checklist (not the signature pages tracker) is the source of truth for that tag. Note: the Item #10 discussed in chm-001061 as retagged/closed (insurance policy assignment/tail coverage) refers to a separate document's Item #10, not this closing set assembly item, which remains Not started pending items 3, 4, and 9.