## Open Items
Item # | Category | Description | Document/Request Ref. | Owner | Status | Date Opened | Follow-Up Due | Notes
1 | Corporate | Confirm good standing certificates for target and all subsidiaries in states of formation | Request List Item 1.3 | Mira Chandrasekhar | In Progress | 2024-05-20 | 2024-06-03 | DE certificate received 5/28; OH secretary of state still outstanding
2 | Contracts | Obtain change-of-control consent analysis for top 10 customer contracts | Request List Item 4.1 | Mira Chandrasekhar | In Progress | 2024-05-20 | 2024-06-05 | 5 of 10 reviewed; consent request sent to Meridian Supply (Contract #7) 5/29 per working session
3 | Contracts | Review Sandhurst-Meridian Supply agreement for anti-assignment clause | Contract #7 | Mira Chandrasekhar | Escalation Resolved | 2024-05-22 | 2024-05-29 | Confirmed clause triggers consent; formal consent request sent to Meridian 5/29, tracked under Item 2 going forward
4 | Real Estate | Confirm leasehold estoppel certificates received from all landlords | Request List Item 6.2 | Mira Chandrasekhar | In Progress | 2024-05-20 | 2024-06-01 | Whitfield resolved (see Item 5); remaining landlords still outstanding
5 | Real Estate | Whitfield Distribution Center - landlord refusing standard estoppel form | Lease Schedule, Property 4 | Mira Chandrasekhar | Resolved | 2024-05-23 | 2024-05-24 | Working session held; landlord's limited liability carve-out accepted as non-material, revised estoppel to be executed this week
6 | Employment | Verify key employee retention agreements executed for Sandhurst management team | Request List Item 8.4 | Mira Chandrasekhar | In Progress | 2024-05-21 | 2024-06-04 | No change since last update; still 2 of 5 executed, awaiting CFO and VP Operations signatures
7 | Intellectual Property | Confirm IP assignment agreements from all current and former engineers | Request List Item 5.6 | Mira Chandrasekhar | Outstanding | 2024-05-20 | 2024-06-06 | No change since last update; gap analysis for pre-2019 assignments not yet started
8 | Litigation | Confirm no undisclosed litigation or threatened claims | Request List Item 9.1 | Mira Chandrasekhar | Resolved | 2024-05-21 | 2024-06-02 | EEOC charge reviewed with client and deemed immaterial to deal terms; no schedule update required
9 | Financial | Reconcile working capital adjustment mechanics against target's QoE report | Request List Item 2.3 | Mira Chandrasekhar | Not Started | 2024-05-24 | 2024-06-07 | No change since last update; still awaiting QoE final draft from accountants
10 | Corporate | Confirm board/stockholder approvals for prior stock option grants | Request List Item 1.9 | Mira Chandrasekhar | Outstanding | 2024-05-20 | 2024-06-03 | No change since last update; cap table discrepancy with board consents still unresolved