## Estoppel Tracker
Counterparty / Lease | Property Address | Request Sent Date | Deadline (per letter) | Draft Received | Final Executed Received | Status | Follow-Up Owner | Notes
Whitcombe Realty Trust | 1420 Corrigan Ave, Sandhurst Facility A | 2025-03-12 | 2025-04-02 | Yes - 2025-03-28 | No | Outstanding - deadline letter sent | I. Solheim | Deadline letter sent per chat; awaiting executed final, draft matches LOI terms
Marlowe Industrial Partners | 88 Ferncrest Rd, Sandhurst Facility B | 2025-03-12 | 2025-04-02 | Yes - 2025-03-25 | Yes - 2025-03-30 | Complete | M. Chandrasekhar | Final matches draft, no discrepancies noted
Kestrel Storage LLC | 215 Union Pkwy, Sandhurst Facility C | 2025-03-14 | 2025-04-04 | No | No | Outstanding - no response | M. Chandrasekhar | Second request needed if no response by 3/31
Danforth Equities | 77 Millrace Dr, Sandhurst Facility D | 2025-03-12 | 2025-04-02 | Yes - 2025-03-29 | No | Outstanding - draft under review | M. Chandrasekhar | Draft has non-standard SNDA carve-out; flag for deal team
Whitcombe Realty Trust (Annex Bldg) | 1424 Corrigan Ave, Sandhurst Facility A-Annex | 2025-03-12 | 2025-04-02 | No | No | Outstanding - deadline letter sent | I. Solheim | Same landlord as Facility A; bundled in deadline letter
Pinegrove Logistics Corp | 509 Harrow St, Sandhurst Facility E | 2025-03-14 | 2025-04-04 | Yes - 2025-03-27 | Yes - 2025-04-01 | Complete | M. Chandrasekhar | Executed version conforms to draft